## Program
P | Campus | ProjectNumber | FUSION # | ProjectDescription | DSA | DSANumber | LEED | LEEDTarget | RecordDrawings | RecordDrawingLocation | GIS | GISComments | Photos | PhotosComments | Minutes | MinutesComments | SoilsReport | SoilsReportComments | Minutes | MinutesComments | OM | OMComments | Warranties | WarrantiesComments | Submittals | SubmittalsComments | Contracts | ContractsComments | BIM | BIMComments | CommissioningReport | CommissioningReportComments | IORReports | IORReportsComments | CCDs | CCDsComments | COBIE | COBIEComments | LEED Cert Received Year | LEED Documentation Letter/Plaque Up? | # Photos in SP | Minutes CM13 vs SP | Labor Warranties Filed / Logged? | Equip O&M's and Warranties Filed / Logged? | Hard-Copy O&M / Warranty Locations | Record BIM Model Received? | Record As-Builts Doc's Logged (w/ specs) | COBiE Info Captured? | CM13 Contracts in SharePoint | CM13 CO's in SharePoint | CO's + CCD's in SharePoint | Evidence of Scope Changes to DSA | Minutes in SharePoint (move from CM13??) | Photos in SharePoint | Have Items Been transferred to Facilities EDMS | IOR (and DSABox) records in SP | All NOC's in SP (and final releases?) | Financial Close-out? | Lessons Learned? | Maint info ID'd (ie Perm BMPs, SF) | Incorporated into Campus Security Plan | RFIs (move from CM13 to SP?) | Submittals? | Project Budget |  | Construction Complete? | Date Construction Complete |  | S - Ballot Reference # | N - Ballot Reference # | On Both Ballots |  | Proj # | DSA_Count | LEED_Count | GIS_Count
N | City | 11110 |  | Humanities Building | Yes | 04-110503 | No | Gold (still "in progress" 9/23/19) | Yes | City: 008-011; 088; 094-095; 097 | Yes | 29 | Yes | 24,905 photos in SP | Yes | 2019-07-01 (Dow) CM13 and SP minutes in combined pdf | Yes | 2020-07-22-test2 | TBD | 1 | Yes | have digital; did not confirm hardcopy yet | TBD | 1 | Yes |  | TBD | 1 | TBD |  | TBD |  | Yes | 542 files in SP (10-15-2019) | TBD |  | TBD | [11 empty] | 75% | [14 empty] | $ 92,478,598 | 1 | Yes | Apr-14 A | 1 | S.I.2 | N.II.1 | x |  | 11110 | 1 | 1 | 1
N | City | 11240 |  | Business Technology Building | Yes | 04-110503 | No | Gold (still "in progress" 9/23/19) | Yes | City: 008-011; 088; 094-095; 097 | Yes | 30 | OK | 80 photos in SP; see 11110 | N A | closed into / combined with #11110 | OK | see Prop N #11110 | TBD | 1 | Yes | have digital; did not confirm hardcopy yet | TBD | TEST | No |  | TBD | 1 | TBD |  | TBD |  | Yes | OK -- project combined with 11110 - 18 files in SharePoint | TBD |  | TBD | [26 empty] | $ 2,151,675 | 1 | Yes | Apr-14 A | 1 | S.I.3 | N.I.3 | x |  | 11240 | 1 | 1 | 1
N | City | 11250 |  | Engineering Technology Building ("T" Building) | Yes | 04-114494 | Yes | Gold (62 points) achieved March 2019 | Yes | combined A-D-T project; did not confirm hardcopy version | TBD | 3 | TBD | 108 photos in SP | Yes | 2019-10-18-AD-T- projects combined. Minutes not in CM13, but are many HP minutes now in SP | Yes | 2019-10-18 - combined A-D-T geotech report - posted to SP | TBD | 1 | Yes | 2019-10-14-digital OM files from Tom F hard drive loaded to SP | Yes | posted to SP on 10-15-2019 | Yes | 2019-10-17 - digital submittals posted to SP | TBD | 1 | TBD |  | TBD |  | Yes | 175 files in SharePoint (combined A-D-T) - 10-15-2019 | TBD |  | TBD | test | [25 empty] | $ 34,722,953 | 0 | Design/Bid | Jul-18 |  | S.I.1 | N.I.2 | x |  | 11250 | 1 | 1 | 1
N | City | 11260 |  | Science Building | No | 04-111042 (certified); 04-117766 (Alts to Science - Not certified) | Yes | Silver | Yes | City-062; 087; 089-090 | Yes | 28 | Yes | 14,908 photos in SP | Yes | 2019-09-18 - CM13 minutes loaded on SP | Yes |  | TBD | 1 | Yes | 2019-10-09 Digital OM's put on SP; See Hardcopy O&M Binders #47 and #48 | Yes | 1 | Yes |  | TBD | 1 | TBD |  | OK | 2019-10-28-TAB report posted on SP | Yes | 957 files in SharePoint | TBD |  | TBD | [26 empty] | $ 57,408,094 | 1 | Yes | Aug-13 A | 1 | S.IV (?) | N.I.1 | x |  | 11260 | 1 | 1 | 1
N | City | 11310 |  | "M" Classroom Building | Yes | 04-112843 | Yes | Silver | Yes | City-015-016 | Yes | 7 | TBD | 344 photos in SP | OK | 2019-10-24: Only PreCon Minutes in CM13; these and some other minutes from Tom's drive loaded to SP -- now uploaded to SP | OK | 2019-10-24 - fault study report located in SP and have hardcopy Bldg M prelim fault study | TBD | 1 | Yes | have digital; did not confirm hardcopy yet | TBD | labor warranties and toilet accessories warranties only on Fac Man SP | Yes |  | TBD | 1 | TBD | test | Yes | is digitally in Fac Man SP | OK | 2019-10-24 some misc testing reports loaded to SP, but consistent IOR reports not located | TBD |  | TBD |  | 2015-03-01 | [5 empty] | City: 21, 22, 23, 24, 26 |  |  |  | Yes |  | reqest to TF 6/17/2015 |  | Yes | 88 |  | No | [7 empty] | $ 9,594,000 | 1 | Yes | Nov-14 A | 1 | S.IV.1 | N.III.3 | x |  | 11310 | 1 | 1 | 1
N | City | 11320 |  | "D" Building Roof | OK | 04-114494 (Certified); 04-116376 (D Fire Alarm in NOT certified as of 3/4/2019) | N A |  | Yes | combined A-D-T project; saved under #11250; did not confirm hardcopy version | TBD | 11 | No | 45 photos in SP | Yes | 2019-10-18-AD-T- projects combined. Minutes not in CM13, but are many HP minutes now in SP | Yes | 2019-10-18 - combined A-D-T geotech report - posted to SP; have hardcopy Bldg D prelim fault study | TBD | 1 | Yes | 2019-10-11-digital OM files from Tom F hard drive loaded to SP | Yes | posted to SP on 10-15-2019 | Yes | 2019-10-17 - digital submittals posted to SP | TBD | 1 | TBD | commenyts | TBD |  | Yes | 175 files in SharePoint (combined A-D-T) - 10-15-2019 | TBD | test 5 | TBD | [26 empty] | $ 4,817,050 | 0 | Design/Bid | Jul-18 |  | S.VI | N.III.4 | x |  | 11320 | 1 | 1 | 1
N | City | 11330 |  | "A" Building Renovation | Yes | 04-114494 | Yes | Gold (61 points) achieved March 2019 | Yes | combined A-D-T project; saved under #11250; did not confirm hardcopy version | TBD | 1 | No | 35 photos in SP | Yes | 2019-10-18-AD-T- projects combined. Minutes not in CM13, but are many HP minutes now in SP | Yes | 2019-10-18 - combined A-D-T geotech report - posted to SP | TBD | 1 | Yes | 2019-10-10-digital OM files from Tom F hard drive loaded to SP | Yes | posted to SP on 10-15-2019 | Yes | 2019-10-17 - digital submittals posted to SP | TBD | 1 | TBD |  | OK | 2019-10-16 - Testing and Balance report in SP | Yes | 175 files in SharePoint (combined A-D-T) - 10-15-2019 | TBD |  | TBD | [26 empty] | $ 24,605,847 | 1 | Design/Bid | Jul-18 |  | S.IV.1 | N.III.1 | x |  | 11330 | 1 | 1 | 1
N | City | 11340 |  | Language/Speech/Visual Arts ("C" Building) | Yes | 04-112710 | Yes | Silver | Yes | City-063-067; 083 | Yes | 5 | No | 77 photos in SP | Yes | 2019-10-24 - not in CM13, but some minutes from Tom F's drive put on SP | Yes | 2019-10-24 - upload to SP | TBD | 1 | Yes | 2019-10-24 - upload to SP | TBD | 1 | Yes |  | TBD | 1 | TBD |  | Yes | is digitally in Fac Man SP | OK | 94 files in SharePoint (10-15-2019) | TBD |  | TBD | [26 empty] | $ 21,128,910 | 1 | Construction | Oct-15 |  | S.V | N.III.2 | x |  | 11340 | 1 | 1 | 1
N | City | 11430 |  | Infrastructure - Central Plant/Sewer & Storm Drain/Data & IT Projects | No | Certfied (04-110878; 04-111010; 04-111216); Not Certified: 04-115435 (Alts to CP) | N A |  | TBD | City-022; digitally have CP and switchgear projects | TBD | Yes for 31 (Central Plant) | Yes | 6,993 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | Yes | Central Plant soils report | TBD | 1 | No | not in SP; ? Hardcopy o&M binder #28 at dsc? | TBD | 1 | TBD |  | TBD | 1 | TBD |  | TBD |  | Yes | 219 files in SharePoint | TBD |  | TBD | [7 empty] | City: 2, 28 | [18 empty] | $ 19,542,870 | 1 | Ongoing | Feb-12 A | 1 | S.VI | N.IV.1 | x |  | 11430 | 1 | 1 | 1
N | Mesa | 12110 |  | Math and Science Building | Yes | 04-111098 | Yes | Silver | Yes |  | No | 75 | Yes | 3,931 photos in SP | Yes | CM13 minutes posted in SP | Yes |  | TBD | 1 | No | 8/29/19: only HVAC/Elec/FA/Security in SP; Hardcopy O&M Binders 8,11,12,20-24,48-50,52 at DSC | TBD | 1 | No | only 3 submittals in SP | TBD | 1 | TBD |  | TBD |  | Yes | 2,177 files in SharePoint | TBD |  | TBD |  | 2014-11-01 | [5 empty] | Mesa: 8, 11, 12, 20, 21, 22, 23, 24 | [18 empty] | $ 106,307,816 | 1 | Yes | Aug-13 A | 1 | S.I.2 | N.I.1 | x |  | 12111; 12110 | 1 | 1 | 1
N | Mesa | 12120 |  | Center for Business and Technology | No | 04-114014 | No | Silver (still "in progress" 9/23/2019) | No |  | No | Fusion # ? | TBD | 758 photos in SP | No | 2019-09-17 - CM13 minutes for red zone meetings - uploaded in CM13 | Yes |  | TBD | 1 | No | not in SP | TBD | 1 | TBD | finishing early 2019 | TBD | 1 | TBD |  | Yes |  | Yes | 281 files in SharePoint | TBD |  | TBD | [26 empty] | $ 32,394,394 | 1 | Design/Bid | Oct-17 |  | N/A | N.I.2 |  |  | 12120 | 1 | 1 | 1
N | Mesa | 12290 |  | LRC Language Labs | Yes | 04-112665 | N A | N/A | Yes | Mesa-024; 030 | Yes | 11 | Yes | 1,845 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | No | no soils report needed? | TBD | 1 | OK | missing plumbing in SP | TBD | 1 | Yes |  | TBD | 1 | TBD |  | TBD |  | TBD | 87 files in SharePoint | TBD |  | TBD | [26 empty] | $ 2,513,000 | 1 | Yes | Aug-13 A | 1 | N/A | N/A |  | 1 | 12290 | 1 | 1 | 1
N | Mesa | 12420 |  | Cafeteria and Bookstore / Stockroom | Yes | 04-112803; 04-115826 | No | Silver (still "in progress" 9/23/2019) | Yes | digital in FacMan SP; hardcopy not confirmed | No | 78 | Yes | 1,905 photos in SP | No | 2019-09-18 - minutes for red zone meetings only in CM13 - uploaded to SP | Yes |  | TBD | 1 | Yes | updated to Fac Man SP; hardcopies not confirmed | OK | many warranties loaded on SP, but not checked at equipment-level | Yes | many loaded and tagged on FM SP | TBD | 1 | TBD |  | TBD |  | Yes | 119 files in SharePoint | Yes | loaded in FM SP | TBD | [26 empty] | $ 44,347,083 | 1 | Construction | Jan-16 |  | N/A | N.II.2 |  |  | 12420 | 1 | 1 | 1
N | Mesa | 12520 |  | Fine Arts and Dramatic Arts | Yes | 04-115516 | OK | Silver (11/07/19: UK got notice of Silver cert, but still pending confirmation on usgbc website) | No |  | No | 38 | No | 11 photos in SP | Yes | 2019-09-18 - CM13 minutes are upload to SP | TBD | project to finish early 2019 | TBD | 1 | No | not in SP | TBD | 1 | Yes | 2019-11-01 - submittals from Tom Fine hard drive uploaded to SP | TBD | 1 | TBD |  | TBD |  | Yes | 390 files in SP (10-15-2019) | TBD |  | TBD | [26 empty] | $ 14,569,538 | 1 | Design/Bid | May-18 |  | N/A | N.I.3 |  |  | 12520 | 1 | 1 | 1
N | Mesa | 12530 |  | Temporary Parking/All Weather Track/Stadium Restroom | Yes | 04-110315; 04-111790; 04-111971 | N A | N/A | TBD | Mesa-031; Restroom as-builts in digital | Yes | 72; 73 (see also proj # 12535) | TBD | 438 photos in SP | Yes | 2019-09-18 - CM13 minutes upload to SP | Yes | 2020-02-11: 2009 Football Field geotech addendum2 on SP | TBD | 1 | No | have restroom OMs only; hardcopy OM binder #14 (global power) | TBD | 1 | TBD | do have restroom submittals (proj #15355) | TBD | 1 | TBD |  | TBD |  | No | 4 files in SharePoint | TBD |  | TBD | [7 empty] | Mesa: 19 | [18 empty] | $ 8,328,634 | 1 | Yes | Aug-12 A | 1 | N/A | N/A |  | 1 | 12530; 12531; 12535 | 1 | 1 | 1
N | Mesa | 12540 |  | Modular Village (Phase 1 & 2) | N A | N/A | N A | N/A | No |  | TBD |  | OK | 140 photos in SP | N A | no minutes in CM13 | OK | temporary | TBD | 1 | N A |  | TBD | 1 | N A |  | TBD | 1 | TBD |  | TBD |  | No | 1 files in SharePoint | TBD |  | TBD | [26 empty] | $ 2,779,115 | 1 | Yes | Oct-10 A | 1 | N/A | N/A |  | 1 | 12540 | 1 | 1 | 1
N | Mesa | 12550 |  | Design Center Renovation (Temporary Technology Village) | Yes | 04-110670 | N A | Not seeking LEED | No | permit dwgs only on SP | No | 67 | TBD | 290 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | OK | temporary | TBD | 1 | N A |  | TBD | 1 | N A |  | TBD | 1 | TBD |  | TBD |  | No | 5 files in SharePoint | TBD |  | TBD | [7 empty] | Mesa: 3 | [18 empty] | $ 5,307,273 | 1 | Yes | Oct-10 A | 1 | N/A | N/A |  | 1 | 12550 | 1 | 1 | 1
N | Mesa | 12600 |  | I-300 Building (Programming/Demolition) | N A | N/A | N A | N/A | N A |  | N A |  | N A | 0 photos in SP | N A | no minutes in CM13 | N A |  | TBD | 1 | N A |  | TBD | 1 | N A |  | TBD | 1 | TBD |  | TBD |  | No | 0 files in SharePoint | TBD |  | TBD | [26 empty] | $ 350,809 | 1 | Yes | Nov-14 A | 1 | N/A | N/A |  | 1 | 12600 | 1 | 1 | 1
N | Miramar | 13110 |  | Library/Learning Resource Center | No | 04-109960 (certified); 04-113743 (not certified) | Yes | Certified | Yes | digital files on SP; confirm hardcopy location | Yes | 54 | TBD | 0 photos in SP, but 134 in IOR SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | Yes | see also Prop S #13110 | TBD | 1 | Yes |  | OK | warranties in Op Manuals | No | minimal submittals only in SP | TBD | 1 | TBD |  | TBD |  | Yes | 1,409 files in SharePoint | TBD |  | TBD | [26 empty] | $ 39,006,991 | 1 | Yes | Jun-12 A | 1 | N/A | N/A |  | 1 | 13110; 13111 | 1 | 1 | 1
N | Miramar | 13150 |  | Arts & Humanities Building & Technology Building | Yes | 04-109543 | Yes | Silver | Yes | digital files on SP; confirm hardcopy location | Yes | 50; 51 | Yes | 2,117 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | Yes |  | TBD | 1 | No | Hardcopy O&M binder #10 at DSC -- is a CD Rom) | TBD | 1 | No | only a handful of submittals on SP; No Elec of HVAC | TBD | 1 | TBD |  | TBD |  | TBD | 68 files in SharePoint - see S | TBD |  | TBD |  | 2011-07-01 | [5 empty] | Miramar: 10 | [18 empty] | $ 31,276,362 | 1 | Yes | Nov-10 A | 1 | N/A | N/A |  | 1 | 13150; 13140 | 1 | 1 | 1
N | Miramar | 13170 |  | Remodel Existing Police Academy (A-200 Building) | Yes | 04-113165 | N A | Not seeking LEED | No |  | Yes | 19 | Yes | 57 photos in SP; 1,265 in IOR SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | Yes |  | TBD | 1 | No |  | TBD | 1 | Yes |  | TBD | 1 | TBD |  | TBD |  | No | 1 file in SharePoint | TBD |  | TBD | [26 empty] | $ 6,200,000 | 1 | Construction | Mar-16 |  | N/A | N/A |  | 1 | 13170 | 1 | 1 | 1
N | Miramar | 13180 |  | EVOC Driving Course | N A | N/A | N A | N/A | N A |  | N A |  | N A | 0 photos in SP | N A |  | N A | site not to be owned by SDCCD | TBD | 1 | N A |  | TBD | 1 | N A |  | TBD | 1 | TBD |  | TBD |  | N A |  | TBD |  | TBD | [26 empty] | $ 5,000,000 | 1 | Future | May-18 |  | N/A | N.I.2 |  |  | 13180 | 1 | 1 | 1
N | Miramar | 13220 |  | Student Services Center (Interim Library) | Yes | 04-112314 | Yes | Silver | Yes | Miramar-006; 055 | Yes | 66 | Yes | 14,260 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | Yes |  | TBD | 1 | No | HVAC in SP only | TBD | 1 | Yes |  | TBD | 1 | TBD |  | TBD |  | TBD | 70 files in SharePoint | TBD |  | TBD |  | 2015-02-01 | [24 empty] | $ 8,050,970 | 1 | Yes | Jun-14 A | 1 | S.IV.3 | N.IV.1 | x |  | 13220 | 1 | 1 | 1
N | Miramar | 13240 |  | Cafeteria/Bookstore & Student/Campus Center | Yes | 04-111062 | No | Silver (still "in progress" 9/23/2019) | Yes | as-builts are in SP; Miramar-021; 024-025; 042-043; 045-052 | Yes | 55 | Yes | 495 photos in SP; 7,512 in IOR SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | Yes |  | TBD | 1 | No | Hardcopy O&M binders #18 at DSC | TBD | 1 | No | ~10 submittals in SP; no HVAC, etc | TBD | 1 | TBD |  | TBD |  | Yes | 1,943 files in SharePoint | TBD |  | TBD | [7 empty] | Miramar: 18 | [18 empty] | $ 39,545,678 | 1 | Yes | Mar-13 A | 1 | N/A | N.IV.2 |  |  | 13240 | 1 | 1 | 1
N | Miramar | 13310 |  | Science Building - Renovate Classrooms to Labs/Add Wing | Yes | 04-112513 | Yes | Silver | No | only MEPF on SP digital; no A etc | No | 68 | Yes | 9,408 photos in SP | No | 2019-09-19 The handful of CM13 minutes available were uploaded to SP | Yes |  | TBD | 1 | Yes |  | TBD | 1 | Yes |  | TBD | 1 | TBD |  | TBD |  | Yes | 1,067 files in SharePoint | TBD |  | TBD |  | 2015-05-01 | [24 empty] | $ 34,418,186 | 1 | Yes | Mar-15 A | 1 | N/A | N.II.1 |  |  | 13310 | 1 | 1 | 1
N | Miramar | 13410 |  | Expand Automotive Technology Career Instructional Building | Yes | 04-109997 | Yes | Gold | Yes | digital files on SP; confirm hardcopy location | Yes | 42 | TBD | 230 photos in SP | No | 2019-09-19 the single CM13 minute posted to SP | Yes | see Prop S #13410; 13130 | TBD | 1 | No | Hardcopy O&M binders #19 at DSC | TBD | 1 | No |  | TBD | 1 | TBD |  | TBD |  | TBD | 29 files in SharePoint | TBD |  | TBD | [7 empty] | Miramar: 19 | [18 empty] | $ 3,493,719 | 1 | Yes | Mar-11 A | 1 | N/A | N.III.3 |  |  | 13410 | 1 | 1 | 1
N | Miramar | 13420 |  | Aviation Maintenance Technology Center | Yes | 04-111402; 04-114653 | Yes | Gold | Yes |  | Yes | 7 | Yes | 1,905 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | Yes |  | TBD | 1 | No |  | TBD | 1 | No | 1 submittal only in SP | TBD | 1 | TBD |  | TBD |  | Yes | 252 files in SharePoint | TBD |  | TBD |  | 2013-03-01 | [24 empty] | $ 10,751,857 | 1 | Yes | Jun-12 A | 1 | S.IV.4 | N.III.1 | x |  | 13420 | 1 | 1 | 1
N | Miramar | 13430 |  | Heavy Duty Advanced Transportation Technology Center | Yes | 04-110830 | Yes | Silver | OK | have all on SP except Intrusion; Miramar-021; 024-025; 042-043; 045-052 | Yes | 59; 60; 61 | Yes | 5,966 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | Yes |  | TBD | 1 | No | Hardcopy O&M binders #15 at DSC | TBD | 1 | Yes |  | TBD | 1 | TBD |  | TBD |  | Yes | 775 files in SharePoint | TBD |  | TBD |  | 2013-10-01 | [5 empty] | Miramar: 15 | [18 empty] | $ 14,371,928 | 1 | Yes | May-13 A | 1 | N/A | N.III.2 |  |  | 13430 | 1 | 1 | 1
N | Miramar | 13540 |  | Parking Structure #1 & Police/Emergency Center | Yes | 04-110654; 04-110712 | Yes | Platinum | Yes | digital in SP; Miramar-016 (record specs not complete for park structure) | Yes | 52; 53 | Yes | 3,965 photos in SP | No | 2019-09-17 no minutes in CM13 | Yes |  | TBD | 1 | No | only fire suppression in SP; Hardcopy O&M binders 3,4,5,30 | TBD | 1 | Yes |  | TBD | 1 | TBD |  | TBD |  | Yes | 638 files in SharePoint | TBD |  | TBD |  | 2012-04-01 | [5 empty] | Miramar: 1, 6 | [18 empty] | $ 15,998,765 | 1 | Yes | Oct-11 A | 1 | N/A | N.IV.3; N.IV.5 |  |  | 13540 | 1 | 1 | 1
N | Miramar | 13550 |  | Campus Safety Enhancements | TBD | N/A | N A | per 10/17/2018 controls meeting | No |  | TBD |  | TBD | 449 photos in SP | No | 2019-09-19 : only 4 design mtng minutes in CM13 - uploaded to SP | OK |  | TBD | 1 | No |  | TBD | 1 | No |  | TBD | 1 | TBD |  | TBD |  | TBD | 37 files in SharePoint | TBD |  | TBD | [26 empty] | $ 446,356 | 1 | Yes | Jun-15 A | 1 | N/A | N.IV.6 |  |  | 13550 | 1 | 1 | 1
N | Miramar | 13630 |  | College Service Center | Yes | 04-11520 | No | Silver (still "in progress" 9/23/2019) | Yes | Site Piping Plan sheet is password-protected | Yes | 56; 57; 58 | Yes | 1,370 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | Yes |  | TBD | 1 | OK | OM's are saved in SP, but may not be complete (i.e. Electrical seems short) | Yes | combined-warranty-file-in-SP | No | several submittals in SP, but no Elec of Plumbing | TBD | 1 | TBD |  | TBD |  | Yes | 314 files in SharePoint | TBD |  | TBD | [26 empty] | $ 5,938,078 | 1 | Yes | Jul-12 A | 1 | N/A | N/A |  | 1 | 13630 | 1 | 1 | 1
N | Miramar | 13650 |  | Expansion of Maintenance Facilities | Yes | 04-113750 | N A | Not seeking LEED | OK | missing FP, Intrusion, and some of Arch -- rest are in SP | TBD |  | TBD | 125 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | Yes |  | TBD | 1 | Yes | in SP | TBD | 1 | No |  | TBD | 1 | TBD |  | TBD |  | No | 0 files in SharePoint | TBD |  | TBD |  | NOT LEED | [24 empty] | $ 3,621,536 | 1 | Construction | Jul-16 |  | N/A | N.IV.4 |  |  | 13650 | 1 | 1 | 1
N | Miramar | 13670 |  | Administration Building | Yes | 04-112383 | Yes | Gold | Yes |  | No | 67 | Yes | 15 photos in SP; 1,346 in IOR SP | No | 2019-09-19 - Only RedZone minutes in CM13 -- posted in SP | Yes |  | TBD | 1 | Yes |  | TBD | 1 | No | only ~5 submittals in SP; no HVAC of plumbing | TBD | 1 | TBD |  | TBD |  | Yes | 175 files in SharePoint | TBD |  | TBD |  | 2015-12-01 | [24 empty] | $ 11,400,000 | 1 | Yes | Jul-14 A | 1 | N/A | N/A |  | 1 | 13670 | 1 | 1 | 1
N | Miramar | 13680 |  | Remodel A-100 Building (CE Classrooms) | Yes | 04-113249 | No | Certified (still "in progress" 9/23/19) | No |  | Yes | 1 | Yes | 5,847 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | Yes |  | TBD | 1 | Yes | OM's Vols1-4 digitally in SP | TBD | 1 | Yes |  | TBD | 1 | TBD |  | TBD |  | Yes | 201 files in SharePoint | TBD |  | TBD | [26 empty] | $ 6,600,000 | 1 | Design/Bid | Jan-17 |  | N/A | N/A |  | 1 | 13680 | 1 | 1 | 1
N | Miramar | 13690 |  | Fire Science and EMT Training Facility | Yes | 04-112341 | No | Silver (still "in progress" 9/23/2019) | Yes | Miramar-009; SP is only missing sheets A-1A101, B-1A1-1, 1A102, 1A103, A-S250, LP502 | TBD |  | Yes | 17,028 photos in SP | No | 2019-09-19 - Only RedZone minutes in CM13 -- posted in SP | Yes | see Cont Ed SP site | TBD |  | Yes |  | TBD | 1 | Yes | see Cont Ed SP site | TBD | 1 | TBD |  | TBD |  | TBD | 40 files in SharePoint | TBD |  | TBD | [26 empty] | $ 16,333,000 | 1 | Yes | Jul-14 A | 1 | S.III.1 | N.I.1 | x |  | 13690 | 1 | 1 | 1
N | CE | 14120 |  | Clairemont/Linda Vista - Land Acquisition & Building (Land $1.8M) | Yes | 04-110938 | Yes | Silver | Yes |  | No |  | Yes | 1,283 photos in SP | No | 2019-09-18 CM13 redzone minutes only; posted on SP | Yes |  | TBD | 1 | No | Hardcopy O&M Binder #1 at DSC | TBD | 1 | OK | submittals in SP seem to be incomplete (i.e. Elec) | TBD | 1 | TBD |  | TBD |  | TBD | 87 files in SharePoint | TBD |  | TBD |  | 2013-01-01 | [24 empty] | $ 22,396,070 |  | Yes | Oct-12 A |  | N/A | N.I.1 |  |  | 14120 | 1 | 1 | 1
N | CE | 14220 |  | Educational Cultural Complex - Phase IIB Wing | No | 04-111330 (main bldg certified; 04-115098 (ceiling work - not certified) | Yes | Silver | Yes | CE-012; 014-015 | No |  | Yes | 3,827 photos in SP | Yes | 2019-09-18 - CM13 minutes loaded to SP | No |  | TBD | 1 | Yes | in SP | Yes | in SP as single file | No |  | TBD | 1 | TBD |  | OK | do have Testing and Balance report in SP | Yes | 436 files in SharePoint | TBD |  | TBD |  | 2014-11-01 | [5 empty] | CE: 8, 9 | [18 empty] | $ 18,686,945 | 1 | Yes | Aug-13 A | 1 | N/A | N.II.1 |  |  | 14220 | 1 | 1 | 1
N | District | 15210 |  | Prop N Program Management | N A | N/A | N A | N/A | N A |  | N A |  | N A |  | N A |  | N A |  | TBD | 1 | N A |  | TBD | 1 | N A |  | TBD | 1 | TBD |  | TBD |  | N A |  | TBD |  | TBD |  | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | $ 51,027,440 |  | N/A | N/A |  | N/A |  |  |  | 15210 | 1 | 1 | 1
N | Reserve | 15220 |  | Proposition N Reserve | N A | N/A | N A | N/A | N A |  | N A |  | N A |  | N A |  | N A |  | TBD | 1 | N A |  | TBD | 1 | N A |  | TBD | 1 | TBD |  | TBD |  | N A |  | TBD |  | TBD | [5 empty] | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | $ 12,611,667 |  | Reserve | N/A |  | N/A | N/A |  |  | 15220 | 1 | 1 | 1
N | Mesa | 123*** |  | Infrastructure - Fire Lane/Central Plant/IT | No | Certfied: 04-112591, 04-112720, 04-113173; Not Certified: 04-111104/07 (PV), 04-117531 (K Alts), 04-117532 (D Alts) | TBD |  | TBD | central plant and signage as-builts saved digitally in SP | TBD | Yes for 71 (Central Plant) | TBD |  | TBD | 1 | Yes | Central Plant soils report | TBD | 1 | TBD | 1 | TBD | 1 | TBD |  | TBD | 1 | TBD |  | TBD |  | No | 28 files in SharePoint total for several Infra projects | TBD |  | TBD | [26 empty] | $ 21,568,549 | 1 | Ongoing | Oct-18 |  | N/A | N.III |  |  | 123*** | 1 | 1 | 1
N | Miramar | 135** |  | Infrastructure - Phase II | No | 04-111114 (PV); 04-113391 (Vernal Pool - not needed?); 04-115610 (wayfinding); 04-116577 (site work) | TBD |  | TBD |  | TBD |  | TBD |  | TBD | 1 | OK |  | TBD | 1 | TBD | 1 | TBD | 1 | TBD | some submittals for 12kV project in SP | TBD | 1 | TBD |  | TBD |  | TBD | multiple projects | TBD |  | TBD | [26 empty] | $ 42,843,305 | 1 | Ongoing | Jul-18 |  | N/A | N.V.1 | x |  | 135** | 1 | 1 | 1
S | City | 11140 |  | Land Acquisition (Career Technology Parcel Land $24.M) | N A | N/A | N A | N/A | N A | see #11220; S | N A |  | N A | 0 photos in SP | N A | 1 | N A | see Prop S #11220 | TBD | 1 | N A |  | TBD | 1 | N A |  | TBD | 1 | TBD |  | TBD |  | TBD | 42 files in SharePoint | TBD |  | TBD |  | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | $ 24,745,904 |  | N/A | N/A |  | N/A | N/A |  | 1 | 11140 | 1 | 1 | 1
S | City | 11210 |  | Child Development Center | TBD | 04-117145 | TBD |  | TBD |  | TBD |  | TBD | 0 photos in SP | TBD | 1 | Yes | digital copy in Fac Man SP site; to construct in 2019 | TBD | 1 | TBD |  | TBD | 1 | TBD | scheduled for 2019 | TBD | 1 | TBD |  | TBD |  | No | 0 files in SharePoint | TBD |  | TBD | [26 empty] | $ 11,023,185 | 1 | Future | Aug-19 |  | S.II.1 | N/A |  |  | 11210 | 1 | 1 | 1
S | City | 11220 |  | Career Technology Center | Yes | 04-108850 | Yes | Gold | Yes | City-019; 021; 026-027; 030; 034; 049-050; 057; 059; 096 | Yes | 24; 25 | Yes | 21,263 photos in SP | Yes | CM13 minutes combined and on SP (8/29/19) | Yes |  | TBD | 1 | No | 2018-12-11: only some plumbing O&Ms on SP | No | 2018-12-11: only some plumbing warranties on SP | Yes |  | TBD | 1 | TBD |  | OK | 2019-10-16 - Testing Air Balance in SP | OK | 33 files in SP (2019-10-16) | TBD |  | OK | 2018-12-11: takeoffs done for P,M,some E | 2011-01-01 | [5 empty] | City 6, 7, 8, 9, 10, 11 |  |  |  | 75% | 83% | [13 empty] | $ 63,313,503 | 1 | Yes | Apr-10 A | 1 | S.III.2 | N/A |  |  | 11220 | 1 | 1 | 1
S | City | 11410 |  | "L" Building Renovation | Yes | 04-106710 | N A | per 10/17/2018 controls meeting | Yes | have digital; confirm hardcopy location | Yes | 4 | Yes | 2,031 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | No | not applicable? | TBD | 1 | No | HVAC only on SP | TBD | 1 | Yes |  | TBD | 1 | TBD |  | TBD |  | No | 9 files in SharePoint | TBD |  | TBD | [11 empty] | 84% | [14 empty] | $ 9,485,942 | 1 | Yes | Apr-09 A | 1 | S.IV.1 | N/A |  |  | 11410 | 1 | 1 | 1
S | City | 11420 |  | "P" Building Renovation | Yes | 04-108775 | Yes | Certified | Yes | 2019-10-09 digital asbuilts put on SP today;record drawing vellums at DSC City #20 -- not on SP | Yes | 2 | Yes | 8,540 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | Yes |  | TBD | 1 | No | HVAC + Elec only on SP | TBD | 1 | Yes |  | TBD | 1 | TBD |  | TBD |  | Yes | 125 files in SharePoint | TBD |  | TBD |  | 2012-08-01 | [24 empty] | $ 10,576,526 | 1 | Yes | Dec-09 A | 1 | S.IV.1 | N/A |  |  | 11420 | 1 | 1 | 1
S | City | 11710 |  | "R" Building Renovation | Yes | 04-107753 | Yes | Silver | Yes | have digital; confirm hardcopy location | Yes | 16 | TBD | 191 photos in SP | No | 2019-09-17 - not in CM13 | No | not applicable? | TBD | 1 | No | not in SP | TBD | 1 | No |  | TBD | 1 | TBD |  | TBD |  | No | 0 files in SharePoint | TBD |  | TBD |  | 2008-04-01 | [24 empty] | $ 3,388,698 | 1 | Yes | Aug-07 A | 1 | N/A | N/A |  | 1 | 11710 | 1 | 1 | 1
S | City | 11720 |  | Modular Village | N A | N/A | N A |  | TBD |  | N A |  | OK | 26 photos in SP | No | 2019-09-17 - not in CM13 | OK | temporary | TBD | 1 | N A | 1 | TBD | 1 | N A |  | TBD | 1 | TBD |  | TBD |  | OK | 0 files in SharePoint | TBD |  | TBD | [26 empty] | $ 1,446,217 | 1 | Yes | Jan-08 A | 1 | N/A | N/A |  | 1 | 11720 | 1 | 1 | 1
S | City | 11810 |  | Land Acquisition + General Purpose Classroom Building (Land $21.8M) | N A | N/A | Yes | Silver | Yes | digital files on SP; confirm hardcopy location | Yes | 26 | Yes | 6,589 photos in SP | No | 2019-09-18 - only a few CM13 minutes - these are posted to SP | Yes |  | TBD | 1 | No | not in SP | TBD | 1 | Yes |  | TBD | 1 | TBD |  | TBD |  | TBD | 65 files in SharePoint | TBD |  | TBD |  | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | $ 80,363,499 |  | Yes | Aug-12 A |  | N/A | N/A |  | 1 | 11810 | 1 | 1 | 1
S | Mesa | 12130 |  | Allied Health Building, Parking and Roadwork | N A | N/A | Yes | Gold | Yes | digital files on SP; confirm hardcopy location | Yes | 68 | TBD | 191 photos in SP | Yes | 2019-09-18 - CM13 minutes posted on SP | Yes |  | TBD | 1 | No | not in SP; hardc Mesa-31,34 - HVAC/Elev only | TBD | 1 | No |  | TBD | 1 | TBD |  | TBD |  | TBD | 37 files in SharePoint | TBD |  | TBD |  | 2010-08-01 | [24 empty] | $ 26,869,668 | 1 | Yes | Aug-09 A | 1 | S.I.3 | N/A |  |  | 12130 | 1 | 1 | 1
S | Mesa | 12210 |  | East Campus Improvement Project and Police Station | Yes | 04-108058; 04-108059; 04-108072; 04-108993; 04-110263 | Yes | Gold | Yes | Mesa-065 | Yes | 69; 70 | Yes | 1,601 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | No |  | TBD | 1 | No | not in SP; HardcopyO&M binder #27 barnhart at DSC | TBD | 1 | No |  | TBD | 1 | TBD |  | TBD |  | TBD | 68 files in SharePoint | TBD |  | TBD |  | 2010-02-01 | [5 empty] | Mesa: 27 |  |  |  | 47% | [14 empty] | $ 34,963,741 | 1 | Yes | Jan-10 A | 1 | S.II | N/A |  |  | 12210 | 1 | 1 | 1
S | Mesa | 12220 |  | Campus Facilities Support Areas | Yes | 04-113884 | N A | Not seeking LEED | Yes | 2019-10-28-Loaded to SP | TBD | 34 (old SSC raquetball courts only?) | TBD | 129 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | Yes |  | TBD | 1 | No | not in SP | TBD | 1 | Yes | 2019-10-29-Loaded to SP | TBD | 1 | TBD |  | Yes | 2019-10-28 - uploaded to SP | Yes | 106 files in SP (10-15-2019; L-200) | TBD |  | TBD | [26 empty] | $ 4,168,253 | 1 | Design/Bid | Nov-16 |  | S.II.5 | N/A |  |  | 12220 | 1 | 1 | 1
S | Mesa | 12250 |  | Renovate Visual Arts Program | Yes | 04-108114 | N A | per 10/17/2018 controls meeting | Yes |  | TBD |  | No | 0 photos in SP | No | 2019-09-17 -not in CM13 | No | no soils report needed? | TBD | 1 | No | not in SP | TBD | 1 | No |  | TBD | 1 | TBD |  | TBD |  | No | 0 files in SharePoint | TBD |  | TBD | [11 empty] | No |  | A | A | No | No |  | No | No | [6 empty] | $ 1,518,626 | 1 | Yes | Sep-07 A | 1 | S.II.5 | N/A |  |  | 12250 | 1 | 1 | 1
S | Mesa | 12320 |  | Humanities, Languages & Multicultural Studies Building | Yes | 04-101936 | N A | per 10/17/2018 controls meeting | Yes |  | TBD |  | TBD | 26 photos in SP | No | 2019-09-17 -not in CM13 | No |  | TBD | 1 | No | not in SP; Hardcopy O&M binders 29/42 at DSC (HVAC only?) | TBD | 1 | No |  | TBD | 1 | TBD |  | TBD |  | No | 0 files in SharePoint | TBD |  | TBD | [7 empty] | Mesa: 29 | [18 empty] | $ 53,175 | 1 | Yes | Feb-03 A | 1 | S.III.2 | N/A |  |  | 12320 | 1 | 1 | 1
S | Mesa | 12410 |  | Student Services Facility | Yes | 04-110328 | Yes | Gold | Yes | Mesa - 046; 050--062; 068-073; 094; 097 | Yes | 74 | Yes | 61,093 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | Yes |  | TBD | 1 | Yes |  | TBD | 1 | Yes |  | TBD | 1 | TBD |  | TBD |  | Yes | 610 files in SharePoint | TBD |  | TBD |  | 2012-12-01 | [24 empty] | $ 44,939,067 | 1 | Yes | Oct-12 A | 1 | S.IV | N/A |  |  | 12410 | 1 | 1 | 1
S | Mesa | 12450 |  | Cogeneration Facility | Yes | 04-106354 | N A | per 10/17/2018 controls meeting | No |  | N A | 2020-02-20 Chris confirmed not applicable | OK | 2020-02-20 Chris M confirmed not needed | OK | 2020-02-20 Chris M confirmed not needed; 2019-09-17 -not in CM13 | No |  | TBD | 1 | OK | 2020-02-20 Chris M confirmed not needed; not in SP | OK | 2020-02-20 -Chris M confirmed not relevant | OK | 2020-02-20 -Chris M confirmed not relevant | TBD | 1 | TBD |  | OK | 2020-02-20 -Chris M confirmed not relevant | OK | 2020-02-20 -Chris M confirmed not relevant; 0 file sin SP | TBD |  | OK | 2020-02-20 -Chris M confirmed not relevant | [10 empty] | 0% | [14 empty] | $ 3,696,342 | 1 | Yes | Jan-05 A | 1 | S.IV.5 | N/A |  |  | 12450 | 1 | 1 | 1
S | Mesa | 12510 |  | Muir Property Acquisition (Land $12.7M) | N A | N/A | N A | N/A | N A |  | TBD |  | No | 0 photos in SP | N A | no minutes in CM13 | N A |  | TBD | 1 | No | not in SP | TBD | 1 | N A |  | TBD | 1 | TBD |  | TBD |  | No | 0 files in SharePoint | TBD |  | TBD |  | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | $ 17,139,697 |  | N/A | N/A |  | N/A | N/A |  | 1 | 12510 | 1 | 1 | 1
S | Mesa | 12721 |  | Social Behavioral Science | Yes | 04-112394 | Yes | Silver | Yes | Mesa-090-092 | Yes | 76 | Yes | 8,255 photos in SP | No | 2019-09-17 - minutes for red zone meetings only in CM13; these are uploaded in SP | Yes |  | TBD | 1 | Yes | divided in SP | TBD | 1 | Yes |  | TBD | 1 | TBD |  | TBD |  | TBD | 79 files in SharePoint | TBD |  | TBD |  | 2015-05-01 | [5 empty] | Mesa: 26 | [18 empty] | $ 40,515,000 | 1 | Yes | Aug-14 A | 1 | S.III.1 | N/A |  |  | 12721; 12723 | 1 | 1 | 1
S | Mesa | 12722 |  | Fitness Center | Yes | 04-112980 | Yes | Silver | Yes | in FacMan SP site; not confirmed hardcopy location | Yes | 77 | Yes | 3,303 photos in SP | No | 2019-09-18 - minutes for red zone meetings in CM13 and uploaded to SP | Yes |  | TBD | 1 | Yes |  | Yes | in FacMan SP site | Yes |  | TBD | 1 | TBD |  | TBD |  | Yes | 350 files in SharePoint | TBD |  | TBD | [26 empty] | $ 15,279,000 | 1 | Construction | Dec-15 |  | S.IV | N/A |  |  | 12722 | 1 | 1 | 1
S | Miramar | 13110 |  | Library/Learning Resource Center - Design | Yes | 04-109960 | N A | see #13110 | N A | see Prop N #13110 | N A |  | TBD | 0 photos in SP, but 134 in IOR SP | N A | closed into N-13110 | Yes | see also Prop N #13110 | TBD | 1 | N A | see Prop N #13110 | TBD | 1 | N A | see Prop N #13110 | TBD | 1 | TBD |  | TBD |  | N A |  | TBD |  | TBD |  | 2015-05-01 | [24 empty] | $ 2,653,044 |  | N/A | N/A |  | S.I.1 | N/A |  |  | 13110; 13111 | 1 | 1 | 1
S | Miramar | 13120 |  | Science & Technology Building (a.k.a Math & Business (?)) | Yes | 04-102836 | Yes | Silver | Yes | have digital; confirm hardcopy location | Yes | 44 | TBD | 272 photos in SP | No | 2019-09-17 no minutes in CM13 | N A | see Prop N #13150 | TBD | 1 | No | plumb _ hvac controls hardcopy O&M binders 29,34 at dsc | TBD | 1 | No |  | TBD | 1 | TBD |  | TBD |  | No | 1 file in SharePoint | TBD |  | TBD | [26 empty] | $ 9,025,573 | 1 | Yes | Feb-05 A | 1 | S.I.2 | N/A |  |  | 13120 | 1 | 1 | 1
S | Miramar | 13135 |  | Technology Building - Design | N A | N/A | N A | see #13150 | TBD |  | N A |  | N A |  | N A | 2019-09-17 no minutes in CM13 | N A | see Prop N #13150 | TBD | 1 | N A |  | TBD | 1 | N A |  | TBD | 1 | TBD |  | TBD |  | N A |  | TBD |  | TBD | [26 empty] | $ 760,871 |  | N/A | N/A |  | S.I.4 | N/A |  |  | 13135 | 1 | 1 | 1
S | Miramar | 13150 |  | Arts & Humanities Building - Design | N A | 04-109543 | N A | see #13150 | N A | see Prop N #13150 | N A | see N-#13150 | Yes | 2,117 photos in SP | N A | 2019-09-17 closed into #13150 Prop N | N A | see Prop N #13150 | TBD | 1 | N A |  | TBD | 1 | N A | see Prop N #13150 | TBD | 1 | TBD |  | TBD |  | TBD | 68 files in SharePoint - see N | TBD |  | TBD |  | 2011-07-01 | [5 empty] | Miramar: 10 | [18 empty] | $ 768,040 |  | N/A | N/A |  | S.IV.2 | N/A |  |  | 13150 | 1 | 1 | 1
S | Miramar | 13210 |  | Hourglass Park Field House | No | 04-107167 | Yes | Certified | Yes | Miramar-026; 054 | Yes | 62; 63; 64; 65 | Yes | 2,861 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | No |  | TBD | 1 | No | Harcopy O&M Binder #20 at DSC | TBD | 1 | No |  | TBD | 1 | TBD |  | TBD |  | No | 17 files in SharePoint | TBD |  | TBD |  | 2009-12-01 | [5 empty] | Miramar: 20, 31 | [18 empty] | $ 22,283,662 | 1 | Yes | Mar-09 A | 1 | S.II.1 | N/A |  |  | 13210 | 1 | 1 | 1
S | Miramar | 13230 |  | Computing & Distribution Center & HVAC Upgrade | No | 04-104134 (not certified as of 1/9/19 - it was before (?)); 04-113689 (certified) | N A | per 10/17/2018 controls meeting | Yes | Miramar-053; 058 | Yes | 43 | No | 0 photos in SP | No | 2019-09-17 no minutes in CM13 | No |  | TBD | 1 | TBD | 1 | TBD | 1 | No | only 1 submittal in SP | TBD | 1 | TBD |  | TBD |  | No | 1 file in SharePoint | TBD |  | TBD | [7 empty] | Miramar: 27, 28, 32, 33 | [18 empty] | $ 7,672,189 | 1 | Yes | Jul-05 A | 1 | S.II.3 | N/A |  |  | 13230 | 1 | 1 | 1
S | Miramar | 13250 |  | Cogeneration Facility | TBD | N/A | N A | per 10/17/2018 controls meeting | OK | digital files on SP of M and E only; confirm hardcopy location | N A | 2020-02-20 Chris confirmed not applicable; 23 (CP); 30 (Pool) | OK | 2020-02-20 Chris M confirmed not needed | OK | 2020-02-20 Chris M confirmed not needed; 2019-09-17 no minutes in CM13 | TBD |  | TBD | 1 | OK | 2020-02-20 Chris M confirmed not needed | OK | 2020-02-20 -Chris M confirmed not relevant | OK | 2020-02-20 -Chris M confirmed not relevant | TBD | 1 | TBD |  | OK | 2020-02-20 -Chris M confirmed not relevant | OK | 2020-02-20 -Chris M confirmed not relevant; 0 files in SP | TBD |  | OK | 2020-02-20 -Chris M confirmed not relevant | [25 empty] | $ 3,566,965 | 1 | Yes | Nov-08 A | 1 | S.II.5 | N/A |  |  | 13250 | 1 | 1 | 1
S | Miramar | 13410; 13130 |  | Automotive Technology Career Instructional Building | Yes | 04-109997 | N A | see N-#13410 | N A |  | N A | see N-#13410 | TBD | 230 photos in SP | No | 2019-09-17 no minutes in CM13 | Yes | see Prop N #13410 | TBD | 1 | No | Hardcopy O&M binders #19 at DSC | TBD | 1 | N A | see Prop N #13410 | TBD | 1 | TBD |  | TBD |  | N A | see # 13410 (N) | TBD |  | TBD |  | 2012-04-01 | [5 empty] | Miramar: 19 | [18 empty] | $ 1,893,176 | 1 | Yes | Mar-05 A | 1 | S.I.3 | N/A |  |  | 13410 | 1 | 1 | 1
S | Miramar | 13511 |  | Infrastructure - Phase I | Yes | 04-108929 | TBD |  | TBD |  | TBD |  | Yes | 3,965 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | OK |  | TBD | 1 | TBD | 1 | TBD | 1 | TBD |  | TBD | 1 | TBD |  | TBD |  | Yes | 206 files in SharePoint - combined with 13514 | TBD |  | TBD | [26 empty] | $ 11,120,157 | 1 | Yes | May-10 A | 1 | N/A | N/A | x | 1 | 13511; 13514 | 1 | 1 | 1
S | Miramar | 13520 |  | Construct "Leave a Legacy Plaza" | TBD | N/A | N A | per 10/17/2018 controls meeting | OK | no record dwgs, but earlier set saved in SP 'MIR 'site' | TBD |  | TBD | 92 photos in SP | No | 2019-09-17 no minutes in CM13 | OK |  | TBD | 1 | TBD | 1 | TBD | 1 | No |  | TBD | 1 | TBD |  | TBD |  | No | 0 files in SharePoint | TBD |  | TBD | [26 empty] | $ 1,311,165 | 1 | Yes | Aug-07 A | 1 | N/A | N/A |  | 1 | 13520 | 1 | 1 | 1
S | Miramar | 13530 |  | Boiler Expansion | TBD | N/A | N A | per 10/17/2018 controls meeting | TBD |  | TBD |  | No | 0 photos in SP | No | 2019-09-17 no minutes in CM13 | OK |  | TBD | 1 | TBD | 1 | TBD | 1 | No |  | TBD | 1 | TBD |  | TBD |  | No | 0 files in SharePoint | TBD |  | TBD | [26 empty] | $ 2,271,840 | 1 | Yes | Mar-06 A | 1 | N/A | N/A |  | 1 | 13530 | 1 | 1 | 1
S | Miramar | 13610 |  | Arts Village | N A | VOID (04-107973) | N A | per 10/17/2018 controls meeting | N A |  | N A |  | N A | 0 photos in SP | N A | 2019-09-17 no minutes in CM13 | N A |  | TBD | 1 | N A |  | N A | 1 | N A |  | TBD | 1 | TBD |  | N A |  | N A | 0 files in SharePoint | TBD |  | N A | [26 empty] | $ 465,392 | 1 | Yes | Jul-06 A | 1 | N/A | N/A |  | 1 | 13610 | 1 | 1 | 1
S | Miramar | 13620 |  | Reprographic/Mailroom Relocation | Yes | 04-109106 | N A | per 10/17/2018 controls meeting | No |  | TBD |  | TBD | 98 photos in SP | Yes | 2019-09-18 - CM13 minutes uploaded to SP | N A |  | TBD | 1 | No |  | TBD | 1 | No |  | TBD | 1 | TBD |  | TBD |  | No | 0 files in SharePoint | TBD |  | TBD | [26 empty] | $ 1,120,915 | 1 | Yes | Mar-09 A | 1 | N/A | N/A |  | 1 | 13620 | 1 | 1 | 1
S | CE | 14110 |  | ECC - Land Acquisition & Relocation Skills Center | Yes | 04-107912 | Yes | Gold | No | may have hardcopy at CE-004; but only permit and addendum sets in SP (5/20/2019) | No |  | Yes | 1,918 photos in SP | No | 2019-09-18 - minutes not in CM13 | Yes | 2020-02-11-hardcopy of soils report scanned and now in SP | TBD | 1 | No |  | TBD | 1 | No |  | TBD | 1 | TBD |  | TBD |  | No | 13 files in SharePoint | TBD |  | TBD |  | 2010-07-01 |  |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A |  | 95% |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | $ 31,731,930 | 1 | Yes | Aug-09 A | 1 | S.I.1 | N/A |  |  | 14110 | 1 | 1 | 1
S | CE | 14210 |  | North City Campus (Land $22M) | Yes | 04-111476 | Yes | Gold | Yes | CE-005 | No |  | Yes | 1,466 photos in SP | Yes | 2019-08-22: CM13 minutes combined into single SP file | Yes | 2020-02-11: both 2008 and 2010 versions in SP | TBD | 1 | Yes | digitally in SP 4/24/19 | Yes | digitally in SP 4/24/19 | N A | see Prop S #14215 | TBD | 1 | TBD |  | TBD |  | Yes | 189 files in SharePoint | TBD |  | TBD |  | 2014-11-01 |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | $ 43,432,099 |  | Yes | Aug-13 A |  | S.II.1 | N/A |  |  | 14210 | 1 | 1 | 1
S | CE | 14215 |  | North City Parking Structure | Yes | 04-111263 | N A | N/A for Parking Structure | No | <CAD files only appear to be on R drive>> | No |  | TBD | 380 photos in SP | No | 2019-09-18 CM13 redzone minutes only | No |  | TBD | 1 | Yes | digitally in SP | TBD | 1 | Yes |  | TBD | 1 | TBD |  | TBD |  | No | 2 files in SharePoint | TBD |  | TBD |  | N/A for Parking Structure | N/A for Parking Structure | [9 empty] | 1 DB contract | 100% | [12 empty] | $ 5,185,821 | 1 | Yes | Dec-11 A | 1 | N/A | N/A |  | 1 | 14215 | 1 | 1 | 1
S | CE | 14310 |  | West City Campus | OK | 04-107524; 04-113290 ("Accepted", although DSA tracker shows a still open 2/8/19) | Yes | Gold | Yes | Record dwgs in SP combined with bid set | No |  | Yes | 7,210 photos in SP | Yes | 2019-08-22: CM13 minutes combined into single SP file | Yes | put in SP 6/10/2019 | TBD | 1 | No | only irrigation in SP; Hardcopy O&M Binders 2--7 at DSC | TBD | 1 | No | only 3 submittals in SP | TBD | 1 | TBD |  | TBD |  | Yes | 164 files in SharePoint | TBD |  | TBD |  | 2010-05-01 | [5 empty] | CE - 2, 3, 4, 5, 6, 7, 11 | [18 empty] | $ 18,199,031 | 1 | Yes | May-09 A | 1 | S.III.1 | N/A |  |  | 14310 | 1 | 1 | 1
S | CE | 14420 |  | Consolidation of Centre City & Cesar Chavez Campus (Land $5.7M) | Yes | 04-111289 | Yes | Silver | No | Some in SP -- but no Arch etc - CE-012; 014-016; 018-020 | No |  | Yes | 1,064 photos in SP | Yes | 2019-08-22: CM13 minutes combined into single SP file | Yes | 2020-02-11 - scanned 2007 prelim geotech to SP | TBD | 1 | Yes |  | Yes |  | Yes |  | TBD | 1 | TBD |  | TBD |  | Yes | 652 files in SharePoint | TBD |  | TBD | [26 empty] | $ 50,037,320 | 1 | Yes | Jul-15 A | 1 | S.IV.1 | N/A |  |  | 14410; 14420 | 1 | 1 | 1
S | CE | 14425 |  | Cesar Chavez Campus Parking Structure | Yes | 04-112885 | N A | N/A for Parking Structure | Yes | in SP ; also CE-008 | No |  | TBD | 498 photos in SP | No | 2019-09-18 - minutes not in CM13 | Yes | includes fault hazard eval | TBD | 1 | Yes |  | Yes |  | Yes |  | TBD | 1 | TBD |  | TBD |  | Yes | 181 files in SharePoint | TBD |  | TBD |  | N/A for Parking Structure | N/A for Parking Structure |  |  | B | B |  | Get Access | Get Access |  |  |  | 2015-11-12 | [12 empty] | $ 7,974,889 | 1 | Yes | May-15 A | 1 | N/A | N/A |  | 1 | 14425 | 1 | 1 | 1
S | CE | 14520 |  | Seismic Retrofit Secondary Effects @ Centre City Skills Center | Yes | 04-103471 | N A | N/A | OK | missing some structural | No |  | No | 0 photos in SP | No | 2019-09-18 - minutes not in CM13 | N A | building built in 1930's or 1940;s | TBD | 1 | No |  | TBD | 1 | OK | no submittals in SP, but building expected to be leased (in 2019) | TBD | 1 | TBD |  | TBD |  | No | 0 files in SharePoint | TBD |  | TBD |  | N/A | [24 empty] | $ 1,551,919 | 1 | Yes | Jan-06 A | 1 | S.V.2 | N/A |  |  | 14520 | 1 | 1 | 1
S | CE | 14610 |  | Mid-City Campus (Land $0.5M) | N A | N/A | N A | N/A | TBD |  | N A |  | TBD | 17 photos in SP | N A | 1 | N A |  | TBD | 1 | N A |  | TBD | 1 | N A |  | TBD | 1 | TBD |  | TBD |  | No | 0 files in SharePoint | TBD |  | TBD |  | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  | Yes | Feb-01 A |  | S.VI | N/A |  |  | 14610 | 1 | 1 | 1
S | CE | 14710 |  | Land Acquisition/Renovation of Building @DSC (Land $5.4M) | N A | N/A | N A | N/A | N A |  | N A |  | N A | 0 photos in SP | Yes | 2019-09-18 - CM13 minutes posted in SP | N A |  | TBD | 1 | N A |  | N A | 1 | N A |  | TBD | 1 | TBD |  | N A |  | N A | 3 files in SharePoint | TBD |  | N A |  | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | $ 7,937,788 |  | Yes | Mar-10 A |  | S.VII | N/A |  |  | 14710 | 1 | 1 | 1
S | District | 14810 |  | Computer Hardware & Software | N A | N/A | N A | N/A | N A |  | N A |  | N A |  | N A | 2019-09-17 no minutes in CM13 | N A |  | TBD | 1 | N A |  | TBD | 1 | N A |  | TBD | 1 | TBD |  | TBD |  | N A |  | TBD |  | TBD |  | N/A |  |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | $ 37,613,379 |  | N/A | N/A |  | S.VIII | N/A |  |  | 14810 | 1 | 1 | 1
S | District | 15110 |  | Prop S Program Management | N A | N/A | N A | N/A | N A |  | N A |  | N A |  | Yes | 2019-09-18 - CM13 minutes posted in SP | N A |  | TBD | 1 | N A |  | TBD | 1 | N A |  | TBD | 1 | TBD |  | TBD |  | N A |  | TBD |  | TBD |  | N/A |  |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | $ 28,324,247 |  | N/A | N/A |  | N/A | N/A |  | 1 | 15110 | 1 | 1 | 1
S | District | 15120 |  | COP Expenditures | N A | N/A | N A | N/A | N A |  | N A |  | N A |  | N A | 1 | N A |  | TBD | 1 | N A |  | TBD | 1 | N A |  | TBD | 1 | TBD |  | TBD |  | N A |  | TBD |  | TBD |  | N/A |  |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | $ 27,761,548 |  | Yes | Aug-07 A |  | N/A | N/A |  | 1 | 15120 | 1 | 1 | 1
S | Reserve | 15130 |  | Proposition S Reserve | N A | N/A | N A | N/A | N A |  | N A |  | N A |  | N A |  | N A |  | TBD | 1 | N A |  | TBD | 1 | N A |  | TBD | 1 | TBD |  | TBD |  | N A |  | TBD |  | TBD |  | N/A |  |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | $ 2,057,299 |  | N/A | N/A |  | N/A | N/A |  | 1 | 15130 | 1 | 1 | 1

## Sample-Equipment
Project # | CSI Div | CSI Description | Sub-Group | Item | Make | Model | O&M | Warranty | Submittals | General vs Fixed-Asset | Asset Tag # | FA Tag # | Building | Fusion # | Floor | Room | Latitude | Longitide | O&M Binder # | Warranty Start | Warranty Duration | Warranty Expires | Item a Consumable ? | Recommend Indiv item Tracking? | Currently Indiv item tracked? | Recommend Waldrop ID Tag? | Currently Waldrop ID Tag? | Contractor | Contract
11110 | 5 | Metals |  | Misc Metal |  |  | Yes | Yes | Yes | [13 empty] | No | No | No | No | No
11110 | 6 | Wood, Plastics, etc. |  | Casework / Shelving / Counters |  |  | Yes | Yes | Yes | [13 empty] | No | Yes | No | No | No
11110 | 7 | Thermal/Moisture-Protect |  | Composite Metal Panel |  |  | No | No | No | [13 empty] | No | Yes | No | No | No
11110 | 7 | Thermal/Moisture-Protect |  | Rain Screen System |  |  | No | No | No | [13 empty] | No | Yes | No | No | No
11110 | 7 | Thermal/Moisture-Protect |  | Roof Accessories (i.e roof ladder; roof hatch) |  |  | N/A | N/A | N/A | [13 empty] | No | Yes | No | No | No
11110 | 7 | Thermal/Moisture-Protect |  | Roofing (PVC) and other |  |  | N/A | N/A | N/A | [13 empty] | No | Yes | No | No | No
11110 | 7 | Thermal/Moisture-Protect |  | Waterproofing (Other) |  |  | OK | OK | OK | [13 empty] | No | Yes | No | No | No
11110 | 7 | Thermal/Moisture-Protect |  | Roof Walking Pad |  |  | OK | OK | OK | [13 empty] | No | No | No | No | No
11110 | 7 | Thermal/Moisture-Protect |  | Solar Glass (see Solar Panels) |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 8 | Openings |  | Access Door |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 8 | Openings |  | Curtain Wall Exterior Window System |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 8 | Openings |  | Doors |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 8 | Openings |  | Hardware - panic devices |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 8 | Openings |  | Overhead coiling doors |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 8 | Openings |  | SolarTubes (Operable and not operable) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 8 | Openings |  | Windows / Glazing |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 8 | Openings |  | Door Hardware - related to FLS; panic hardware/ elec door holdopens / (see also ADA access buttons) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 9 | Finishes |  | Paint (use for take-off SF estimates of paint?? - planning) |  |  | TBD | TBD | TBD | [13 empty] | Yes | Yes | No | No | No
11110 | 9 | Finishes |  | Anti-Graffiti Coating |  |  | TBD | TBD | TBD | [13 empty] | Yes | No | No | No | No
11110 | 9 | Finishes |  | Acoustic Panel Ceiling |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 9 | Finishes |  | Flooring - carpet |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | no
11110 | 9 | Finishes |  | Flooring - other |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 9 | Finishes |  | Flooring - vct |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 9 | Finishes |  | Wall covering (fabric vs frp etc) - track manufacturer |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 10 | Specialties | Restroom | Paper Towel Dispenser |  |  | TBD | TBD | TBD | [13 empty] | Yes | No | No | No | No
11110 | 10 | Specialties | Restroom | Soap Dispenser |  |  | TBD | TBD | TBD | [13 empty] | Yes | No | No | No | No
11110 | 10 | Specialties | Restroom | Toilet Paper Dispenser |  |  | TBD | TBD | TBD | [13 empty] | Yes | No | No | No | No
11110 | 10 | Specialties | Restroom | Toilet Seat Cover Dispenser |  |  | TBD | TBD | TBD | [13 empty] | Yes | No | No | No | No
11110 | 10 | Specialties | Restroom | Elec Hand Dryer |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 10 | Specialties | Restroom | Sanitary Napkin/Tampon Dispenser |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 10 | Specialties | Restroom | Toilet & Urinal Compartments / Bathroom Stalls |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 10 | Specialties | Restroom | Baby Changing Apparatus in Bathroom |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 10 | Specialties | Restroom | ADA Bathroom Grab Bars |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 10 | Specialties | Restroom | Bathroom trash can (recessed) |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 10 | Specialties | Restroom | Mirror |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 10 | Specialties |  | Tack Board - small |  |  | TBD | TBD | TBD | [13 empty] | Yes | No | No | No | No
11110 | 10 | Specialties |  | White Boards - small |  |  | TBD | TBD | TBD | [13 empty] | Yes | No | No | No | No
11110 | 10 | Specialties |  | Fire Extinguishers /FE Cabinets |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | No
11110 | 10 | Specialties |  | Modular Office Walls |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 10 | Specialties |  | Fire Curtain / Fire Wall |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | Yes
11110 | 10 | Specialties |  | Defibrillator Cabinets |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 10 | Specialties |  | Display Case (i.e. Recessed Display Case / Lockable) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 10 | Specialties |  | Operable Wall |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | Yes
11110 | 10 | Specialties |  | Signage - Egress |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 10 | Specialties |  | Tack Board - large |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 10 | Specialties |  | White Boards - large |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 10 | Specialties |  | Parking Signage (incl ADA) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 10 | Specialties |  | Emergency Key Cabinets (i.e. Knox-Box) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 10 | Specialties |  | Corner Guard / Wall Guard |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 10 | Specialties |  | Locker room benches |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 10 | Specialties |  | Signage - Directional |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 10 | Specialties |  | Signage - Rooms |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 11 | Equipment | Classroom | Fixed Projection Screens (motorized and manual) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 11 | Equipment | Food-Service | Glove dispesner |  |  | TBD | TBD | TBD | [13 empty] | Yes | No | No | No | No
11110 | 11 | Equipment | Food-Service | Coffee Maker (i.e. Airpot; Expresso Machine/Grinder) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 11 | Equipment | Food-Service | Dishwasher |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 11 | Equipment | Food-Service | Food Service Equipment (Other / Specialized) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 11 | Equipment | Food-Service | Freezer / Walk-in Cooler -- Fixed |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | Yes
11110 | 11 | Equipment | Food-Service | Freezer / Walk-in Cooler -- Non-Fixed |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 11 | Equipment | Food-Service | Ice Maker |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 11 | Equipment | Food-Service | Microwave |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 11 | Equipment | Food-Service | Mixer/Blender |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 11 | Equipment | Food-Service | Prep Sink |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 11 | Equipment | Food-Service | Oven |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | Yes
11110 | 11 | Equipment | Food-Service | POS cash register / point of sale |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 11 | Equipment | Food-Service | Water Filration System |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 11 | Equipment | Food-Service | Food Service Sinks / Dipperwell Assembly |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 11 | Equipment | Food-Service | Freezer Merchandiser |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 11 | Equipment | Food-Service | Garbage disposer |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 11 | Equipment | Food-Service | Hot cabinets |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 11 | Equipment | Food-Service | General food service millwork |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 11 | Equipment |  | Parking Control Equipment (i.e. Parking Permit Machine) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | Yes
11110 | 11 | Equipment |  | Cabinets (with drawers/doors) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 11 | Equipment |  | Counters (with drawers/doors) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 11 | Equipment |  | Employee lockers |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | Yes
11110 | 11 | Equipment |  | Faucet |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 11 | Equipment |  | Grease Interceprtor |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 11 | Equipment |  | Hot water heater |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 11 | Equipment |  | Knock Box |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 11 | Equipment |  | Window Washing Davit Base |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 11 | Equipment |  | Window Washing Equipment |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 12 | Furnishings | Office | Systems Furniture / Cubicles |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 12 | Furnishings | Site | Bench |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 12 | Furnishings | Site | Bike Rack |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 12 | Furnishings | Site | Bus Shelter |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 12 | Furnishings | Site | Picnic Table |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 12 | Furnishings | Site | Site Furnishings: Trash Can ' Litter Receptacle |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 12 | Furnishings |  | Furniture - Other |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 12 | Furnishings |  | Modular Canopy Shades |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 12 | Furnishings |  | Portable table with stacking chairs |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 12 | Furnishings |  | Auditorium Seating |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 12 | Furnishings |  | Blinds /Shades / Curtains (Window Covering) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 12 | Furnishings |  | Student Chairs |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 12 | Furnishings |  | Student Desks |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 12 | Furnishings |  | Walk off Mat |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 12 | Furnishings |  | Stadium Seating |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 14 | Conveying-Equip |  | Elevator |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 14 | Conveying-Equip |  | Elevator Room Equipment |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 14 | Conveying-Equip |  | Wheelchair Lift |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 21 | Fire-Suppression |  | Fire Hydrant |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 21 | Fire-Suppression |  | Backflow Device |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 21 | Fire-Suppression |  | Fire Sprinkler Heads |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 21 | Fire-Suppression |  | Fire Protection Standpipe Control Valve; Zone Control Riser Valve Assembly |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 22 | Plumbing |  | Condensate Pump / Pump Sched Info |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 22 | Plumbing |  | Domestic Water storage tank on roof; tower |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 22 | Plumbing |  | Hot Water Circ Pump / Pump Sched Info |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 22 | Plumbing |  | Drinking Fountains (ADA etc) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 22 | Plumbing |  | Toilet / Water Closet |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 22 | Plumbing |  | Drinking Fountain - Electric |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 22 | Plumbing |  | Mop Sink / Floor Sink |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 22 | Plumbing |  | Gas Meter |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 22 | Plumbing |  | Hose Bibb |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 22 | Plumbing |  | Lavatory (Bathroom as a Unit to be tracked) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 22 | Plumbing |  | Roof drain / roof receptor |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 22 | Plumbing |  | Sink - Classroom |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 22 | Plumbing |  | Sink - Kitchenette |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 22 | Plumbing |  | Urinal |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 22 | Plumbing |  | Valves (inside/outside) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 22 | Plumbing |  | Water Closet |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 22 | Plumbing |  | Boiler & tank; Water Heater (see Water Heater Schedule) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 22 | Plumbing |  | Water Meter |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 22 | Plumbing |  | Floor Drain |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 22 | Plumbing |  | CHWP (Chilled Water Pipe) |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 22 | Plumbing |  | HWP (Hot Water Pipe) |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 22 | Plumbing |  | Piping, etc |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 23 | HVAC |  | Filters |  |  | TBD | TBD | TBD | [13 empty] | Yes | Yes | Yes | No | No
11110 | 23 | HVAC |  | AH - Air Handling Unit - see AHU Schedule |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | Air Cooled Chiller - CH |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | Air Separator Schedule - AS |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | Chilled Water Pump |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | Condensing Unit |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | Controls Panel |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | CWST (ST) - Chilled Water Storage Tank |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | Exhast Fan - EF |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | Expansion Tank - ET |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | Hot Water Pump |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | Sensor |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | Split System - CU (Outside) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | Split System - FC (Inside) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | Thermostats |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | VAV - Variable Air Volume Terminal Schedule |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | Volume Damper |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 23 | HVAC |  | Operable Gate in Mechanical Screen |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 23 | HVAC |  | Performance Cert of Compliance Data - HVAC Zones -- See 04-110817 Mech Sheets |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 23 | HVAC |  | Cert of Compliance Data - Energy Checklist - Opaque Surfaces -- See 04-110817 Mech Sheets |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 23 | HVAC |  | Diffusers - Exhaust Air |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 23 | HVAC |  | Diffusers - Return Air |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 23 | HVAC |  | Diffusers - Supply Air |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 23 | HVAC |  | Fire Smoke Dampers |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 23 | HVAC |  | Roof Curbs |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 23 | HVAC |  | Exterior Ductwork |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 23 | HVAC |  | Exterior Grilles |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 26 | Electrical |  | UPS - Uninteruptable Power Supply |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 26 | Electrical |  | Washing Machine / Dryer |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 26 | Electrical |  | Electric Meter |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 26 | Electrical |  | Elevator Smoke Door |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 26 | Electrical |  | Lighting Control Panel; Network Lighting Controls |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 26 | Electrical |  | Bloom boxes - power |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 26 | Electrical |  | SDGE Box |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 26 | Electrical |  | Street Light / Pathway Light |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 26 | Electrical |  | Dedicated Power for BTU Meter (Gas Meter) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 26 | Electrical |  | Egress / Emergency Lighting |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | Yes
11110 | 26 | Electrical |  | Elec hand wash / sink |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 26 | Electrical |  | Electrical Cabinets and Enclosures |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 26 | Electrical |  | Lighting Fixtures; Luminaire Schedule |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 26 | Electrical |  | Lighting Inverter |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 26 | Electrical |  | Panel Boards |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 26 | Electrical |  | Switchboards; Wall-Mounted Panelboards |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 26 | Electrical |  | Transformer |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 26 | Electrical |  | TVSS - Transient Voltage Surge Suppressor |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 26 | Electrical |  | Solar Panels |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 26 | Electrical |  | Junction Boxes |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 26 | Electrical |  | Substation?? |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 26 | Electrical |  | Elec outlets / power outlets |  |  | TBD | TBD | TBD | [13 empty] | No | ? | No | No | No
11110 | 26 | Electrical |  | Wall Switch |  |  | TBD | TBD | TBD | [13 empty] | No | ? | No | No | No
11110 | 26 | Electrical |  | Cert of Compliance - Indoor Lighting (see 04-110817 E Sheets) |  |  | TBD | TBD | TBD | [13 empty] | No | ? | No | No | No
11110 | 26 | Electrical |  | Cert of Compliance - Outdoor Lighting (see 04-110817 E Sheets) |  |  | TBD | TBD | TBD | [13 empty] | No | ? | No | No | No
11110 | 27 | Communications (…AV) |  | Assisted Listening System Receivers |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 27 | Communications (…AV) |  | Projector (LCD - Ceiling Mounted) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 27 | Communications (…AV) |  | Teaching Podium Control Stations |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 27 | Communications (…AV) |  | Television / Monitor |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 27 | Communications (…AV) |  | Clocks |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 27 | Communications (…AV) |  | Public Announcement System |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 27 | Communications (…AV) |  | BlueRay/DVD/Video Streamer |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | Yes | ?
11110 | 27 | Communications (…AV) |  | LCD Screens / Digital Signage |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 27 | Communications (…AV) |  | Data Outlet |  |  | TBD | TBD | TBD | [13 empty] | No | No | ? | No | No
11110 | 28 | Elec-Safety/Security | Fire | Heat Detector |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security | Fire | Horn/Strobe |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security | Fire | Manual Pull Stations |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security | Fire | Mini Horn |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security | Security | Motion Detector |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security | Security | Panic Switch |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security |  | Battery Backup -- see UPS |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 28 | Elec-Safety/Security |  | Card Reader / Security / Keypad |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 28 | Elec-Safety/Security |  | Door Contact |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 28 | Elec-Safety/Security |  | Fire Alarm LCD Annunciator Panel; Notifier Panels |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 28 | Elec-Safety/Security |  | Fire Sprinkler System (Existence of in Building) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 28 | Elec-Safety/Security |  | Security Alarm/Keypad |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 28 | Elec-Safety/Security |  | Smoke Guard |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 28 | Elec-Safety/Security |  | Access Control Panel |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 28 | Elec-Safety/Security |  | Emergency Telephone Box; Emergency Wall Phone |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 28 | Elec-Safety/Security |  | Fire Alarm Relays |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 28 | Elec-Safety/Security |  | Fire Alarm Transponder |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 28 | Elec-Safety/Security |  | Fire Smoke Dampers |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 28 | Elec-Safety/Security |  | Fire Sprinkler Control Panel |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 28 | Elec-Safety/Security |  | Carbon Dioxide Sensor |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security |  | FACP - Fire Alarm Control Panel |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security |  | FATC - Fire Alarm Terminal Cabinet |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security |  | Fire Strobes |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security |  | FSCP - Firefighter's Smoke Control Panel |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security |  | Knox Box |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security |  | Pre-Action Release Panel |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security |  | Projector Alarm with Relay |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security |  | SCDC - Smoke Control Damper Cabinet |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security |  | SCTC - Smoke Control Terminal Cabinet |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security |  | Security Cameras (CCTV?) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 28 | Elec-Safety/Security |  | Smoke Detectors |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 31 | Earthwork |  | Retaining Walls |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 31 | Earthwork |  | Caissons |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Site benches |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | No
11110 | 32 | Ext-Improvements |  | Exterior kiosk |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 32 | Ext-Improvements |  | ADA Curb Ramps |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 32 | Ext-Improvements |  | ADA Ramps |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 32 | Ext-Improvements |  | Traffic Control - Signs/Speed Bumps |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 32 | Ext-Improvements |  | Trees |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 32 | Ext-Improvements |  | Motorized Gate / Controllers |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 32 | Ext-Improvements |  | Parking sensors |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | No | No
11110 | 32 | Ext-Improvements |  | Patio furniture |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 32 | Ext-Improvements |  | Backflow Device |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 32 | Ext-Improvements |  | Flow Sensor |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 32 | Ext-Improvements |  | Irrigation Controller |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 32 | Ext-Improvements |  | Irrigation Heads/Bubblers |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 32 | Ext-Improvements |  | Irrigation Meter |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 32 | Ext-Improvements |  | Irrigation Valves - in General |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 32 | Ext-Improvements |  | Exterior Temperature Sensor |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 32 | Ext-Improvements |  | Curb and Gutter |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Curb Ramps |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Driveway/Hardscape/Pavers |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Downspouts |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Fence |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Irrigation Valves (Air Relief Valve) |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Irrigation Valves (Ball Valve) |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Irrigation Valves (Master Control) |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Irrigation Valves (Quick Coupler Valve) |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Irrigation Valves (Remote Control) |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Asphalt |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Bollards |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Gate - Non-Motorized |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Iron Fencing |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Parking Stops |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 32 | Ext-Improvements |  | Sidewalk / Exterior |  |  | TBD | TBD | TBD | [13 empty] | No | No | No | No | No
11110 | 33 | Utilities |  | Exterior Drain |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 33 | Utilities |  | Sewer Lateral |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 33 | Utilities |  | Sewer Line |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 33 | Utilities |  | Sewer Manhole/Box |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 33 | Utilities |  | Storm Drain |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 33 | Utilities |  | Storm Drain Manhole/Box |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 33 | Utilities |  | SWPPP BMP's |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 33 | Utilities |  | Water Lateral |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 33 | Utilities |  | Water Line |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 33 | Utilities |  | Water Meter Box |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 33 | Utilities |  | Gas Meters |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | No
11110 | 33 | Utilities |  | Items with Pilot Lights (need to get re-lit after gas shutdown) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 33 | Utilities |  | Water Valve - types |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 44 | Pollution/Waste-Equip |  | HazMat Storage |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | Yes
11110 | 45 | Industry | Science | Equipment - Science - Chemistry |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 45 | Industry | Science | Equipment - Science - Other |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 45 | Industry | Science | Equipment - Science - Astronomy |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 45 | Industry | Science | Equipment - Science - Biology |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 45 | Industry | Science | Equipment - Science - Cadaver / Equip |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | Yes | No
11110 | 45 | Industry |  | Fume Hoods |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | No
11110 | 45 | Industry |  | Equipment - Sewing |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 45 | Industry |  | Equipment - Auto |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 45 | Industry |  | Equipment - Educational Electrical |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 45 | Industry |  | Equipment - Educational HVAC |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 45 | Industry |  | Equipment - Educational IT/GIS |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 45 | Industry |  | Equipment - Fine Art (i.e. Kilns) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 45 | Industry |  | Equipment - Fitness / Exercise |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 45 | Industry |  | Equipment - Manufacturing Machinery |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 45 | Industry |  | Equipment - Medical / Dental |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | 45 | Industry |  | Equipment - Agriculture (Greenhouse) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 45 | Industry |  | Equipment - Animal Health |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 45 | Industry |  | Equipment - Aviation |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 45 | Industry |  | Equipment - Cosmotology / Fashion |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 45 | Industry |  | Equipment - Culinary |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 45 | Industry |  | Equipment - Fire EMT |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 45 | Industry |  | Equipment - Photography |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 45 | Industry |  | Equipment - Radio Station |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 45 | Industry |  | Equipment - Educational - Other |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 45 | Industry |  | Equipment - Theatre / Costuming |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 45 | Industry |  | Equipment - TV Studio |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 45 | Industry |  | Equipment - EVOC |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 45 | Industry |  | Emergency Eyewash Stations (2/26/18 CW says no systematic plan to check on jobwalk) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | No | Yes | No
11110 | 45 | Industry |  | Equipment - Sports (i.e. Pole Vault Mats) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | 45 | Industry |  | Equipment - Music |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | Yes | No
11110 | 45 | Industry |  | Chemical Shelf / Storage Cabinet for Flammable Storage |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | ? | No | No
11110 | A-50 | Furniture |  | filing cabinets |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | A-50 | Furniture |  | tables |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | A-50 | Furniture |  | desks |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | A-50 | Furniture |  | chairs |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | A-51 | Info-Tech |  | desk-lights |  |  | TBD | TBD | TBD | [13 empty] | Yes | No | No | No | No
11110 | A-51 | Info-Tech |  | keyboards / mice |  |  | TBD | TBD | TBD | [13 empty] | Yes | No | No | No | No
11110 | A-51 | Info-Tech |  | computers |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | A-51 | Info-Tech |  | servers |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | A-51 | Info-Tech |  | printers / copiers / scanners |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | A-51 | Info-Tech |  | server UPS |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | ?
11110 | A-51 | Info-Tech |  | software |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | No | ?
11110 | A-52 | Police Equip |  | Weapons |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | ?
11110 | A-53 | M&O Equip |  | Tools (over $200) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | No
11110 | A-53 | M&O Equip |  | compressors |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | No
11110 | A-53 | M&O Equip |  | Forklifts, etc (DSC); cranes |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes
11110 | A-54 | Vehicles |  | Cars / Carts (DSC) |  |  | TBD | TBD | TBD | [13 empty] | No | Yes | Yes | Yes | Yes

## Image
S. Dow
| CLOSEOUT COMPLETION |  | DSA Cert? |  |  | LEED Cert? |  |  | GIS updated? |  | Commissing Reoprt | 2018-06-14
Complete?
Yes
No
No, but OK
N/A
Still checking
|  |  | click opens: list of each project with prop, Campus, Proj #, project name, DSA #, Date Certified, Status |  |  | click opens: list of each project with prop, Campus, Proj #, project name, LEED Target, Date Obtained, Status |  |  | click opens: list of each project with prop, Campus, Proj #, project name, GIS No. or Fusion #, Status |  | click opens: list of each project with prop, Campus, Proj #, project name, Commissioning Company, Date of Report, Status
| Photos in SP? |  | Minutes on File? |  |  | Soils Report |  |  | BIM ? |  | IOR Docs in SP?
click opens: list of each project with prop, Campus, Proj #, project name, # photos in SP, Status |  |  | click opens: list of each project with prop, Campus, Proj #, project name, # minutes in CM13(?) , # minutes in SP, Status |  |  | click opens: list of each project with prop, Campus, Proj #, project name, Soils Company, Date of Report, Status |  |  | click opens: list of each project with prop, Campus, Proj #, project name, BIM non-corrupted, located, major trades included?, Status |  | click opens: list of each project with prop, Campus, Proj #, inspector name, inspector reports available, testing reports available, Status
| Permit Dwgs/Specs |  | Record Dwgs/Specs |  |  | Equip O&M |  |  | Equip Warranties |  | Submittals
click opens: list of each project with prop, Campus, Proj #, project name, date agency approval, agency, broken out in Fac SP? , Status |  |  | click opens: list of each project with prop, Campus, Proj #, project name, broken out in Fac SP? , date of as-built, hardcopy archive location, Status |  |  | click opens: PIE chart of status per project; upon click, show list of Trade per CSI, provider, date of O&M, O&M location, Status |  |  | click opens: PIE chart of status per project; upon click, show list of Trade per CSI, provider, date of warranty, warranty duration, warranty expires, Status |  | click opens: PIE chart of status per project; upon click, show list of Trade per CSI, provider, date of submittal, Status
|  | NOTES: | DO INCLUDE | CM13 Contracts in SharePoint | CM13 CO's in SharePoint | COBiE Info Captured? | All NOC's in SP (and final releases?)
|  |  | DO NOT INCLUDE | Have Items Been transferred to Facilities EDMS | Financial Close-out? | Lessons Learned? | Maint info ID'd (ie Perm BMPs, SF) | Incorporated into Campus Security Plan | Evidence of Scope Changes to DSA | CO's + CCD's in SharePoint
Contracts

## FM-SP-Summary
Campus | Prop | Proj # | Project Name | Addendum | Agency/Form | Agenda/Minutes | Budget/Costs | Change Order | Contract | Correspondence | Design Comment | Dwg-01-Pre-Approved | Dwg-02-Permit | Dwg-03-AsBuilt/Record | Dwg-04-FF&E | Dwg-05-Other | Invoice | Legal | O&M Manual | Report-Commissioning | Report-Environmental | Report-GeoTech | Report-HazMat | Report-Inspection/Test | Report-Other | RFI | Schedule | Scope Document | Spec-01-Pre-Approved | Spec-02-Permit | Spec-03-AsBuilt/Record | Spec-04-FF&E | Spec-05-Other | Submittal/Shop | Sustainability | Warranty
City | N | 11110 | Humanities Building | [12 empty] | 1 | [5 empty] | 1 |  |  | 1 | [8 empty] | 1
City | S | 11140 | Land Acquisition (Career Technology Parcel Land $24.M)
City | S | 11210 | Child Development Center
City | S | 11220 | Career Technology Center | [10 empty] | 1 | 1 | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [8 empty] | 1 |  | 1
City | N | 11240 | Business Technology Building
City | N | 11250 | Engineering Technology Building ("T" Building) | [9 empty] | 1 | [16 empty] | 1
City | N | 11260 | Science Building | [9 empty] | 1 |  |  | 1 | [5 empty] | 1 | [7 empty] | 1 |  |  |  | 1
City | N | 11310 | "M" Classroom Building | [30 empty] | 1
City | N | 11320 | "D" Building Roof
City | N | 11330 | "A" Building Renovation
City | N | 11340 | Language/Speech/Visual Arts ("C" Building) | [30 empty] | 1
City | S | 11410 | "L" Building Renovation | [9 empty] | 1 | 1 |  | 1 |  |  | 1 | [5 empty] | 1 | [8 empty] | 1 |  | 1
City | S | 11420 | "P" Building Renovation | [9 empty] | 1 | [5 empty] | 1 |  |  | 1 |  |  | 1 | [8 empty] | 1 |  | 1
City | N | 11430 | Infrastructure - Central Plant/Sewer & Storm Drain/Data & IT Projects | [9 empty] | 1 | 1 | [7 empty] | 1 | [7 empty] | 1 |  |  |  | 1
City | S | 11710 | "R" Building Renovation | [10 empty] | 1
City | S | 11720 | Modular Village
City | S | 11810 | Land Acquisition + General Purpose Classroom Building (Land $21.8M) | [9 empty] | 1 | 1 |  | 1 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 1
City |  | SITE | [10 empty] | 1 | 1 |  | 1 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  | 1
Mesa | N | 12110 | Math and Science Building | [9 empty] | 1 |  |  | 1 |  |  | 1 | 1 | [9 empty] | 1
Mesa | N | 12120 | Center for Business and Technology | [9 empty] | 1 | [8 empty] | 1 | [7 empty] | 1
Mesa | S | 12130 | Allied Health Building, Parking and Roadwork | [10 empty] | 1 | 1 | 1 | [5 empty] | 1 | [7 empty] | 1
Mesa | S | 12210 | East Campus Improvement Project and Police Station | [12 empty] | 1 | [16 empty] | 1
Mesa | S | 12220 | Campus Facilities Support Areas | [9 empty] | 1 |  |  | 1 | [5 empty] | 1 | 1 |  | 1 |  |  |  |  | 1 |  |  | 1
Mesa | S | 12250 | Renovate Visual Arts Program
Mesa | N | 12290 | LRC Language Labs | [12 empty] | 1 |  |  | 1 | 1 | [12 empty] | 1 | 1 |  | 1
Mesa |  | 123102 | [11 empty] | 1 |  | 1 | [16 empty] | 1 | 1
Mesa |  | 123103 | [10 empty] | 1 | 1 |  |  |  |  | 1 | 1 |  | 1 |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1
Mesa |  | 12315 | [11 empty] | 1
Mesa | S | 12320 | Humanities, Languages & Multicultural Studies Building
Mesa | S | 12410 | Student Services Facility | [9 empty] | 1 | [5 empty] | 1 | 1 |  | 1 | [7 empty] | 1 | 1 |  | 1 | 1
Mesa | N | 12420 | Cafeteria and Bookstore / Stockroom | [9 empty] | 1 | [7 empty] | 1 | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 1
Mesa | S | 12450 | Cogeneration Facility
Mesa | S | 12510 | Muir Property Acquisition (Land $12.7M)
Mesa | N | 12520 | Fine Arts and Dramatic Arts | [9 empty] | 1 | [9 empty] | 1
Mesa | N | 12530 | Temporary Parking/All Weather Track/Stadium Restroom | [9 empty] | 1 | [8 empty] | 1 | [7 empty] | 1
Mesa | N | 12535 | [11 empty] | 1 |  |  |  |  | 1 | [14 empty] | 1 |  | 1
Mesa | N | 12540 | Modular Village (Phase 1 & 2)
Mesa | N | 12550 | Design Center Renovation (Temporary Technology Village) | [9 empty] | 1 |  |  | 1 | [16 empty] | 1
Mesa | N | 12600 | I-300 Building (Programming/Demolition)
Mesa | S | 12721 | Social Behavioral Science | [10 empty] | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  | 1
Mesa | S | 12722 | Fitness Center | [8 empty] | 1 | 1 |  |  | 1 |  |  |  | 1 |  | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  | 1 | 1 |  | 1
Mesa |  | 12723 | [13 empty] | 1 |  |  | 1 | [13 empty] | 1 | 1 |  | 1
Mesa |  | SITE | [9 empty] | 1 | 1 | 1 |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 1 |  |  | 1 | 1 |  | 1
Miramar | S; N | 13110 | Library/Learning Resource Center | [9 empty] | 1 | 1 |  | 1 |  |  | 1 |  |  | 1 |  | 1 | [5 empty] | 1 | 1 |  |  | 1 |  | 1
Miramar | S | 13120 | Science & Technology Building | [9 empty] | 1 | 1
Miramar |  | 13130 | [10 empty] | 1 | [8 empty] | 1 | [7 empty] | 1
Miramar | S | 13135 | Technology Building - Design
Miramar | S; N | 13150 | Arts & Humanities Building & Technology Building | [9 empty] | 1 | 1 | [7 empty] | 1 | [7 empty] | 1 |  | 1 |  | 1
Miramar | N | 13170 | Remodel Existing Police Academy (A-200 Building) | [9 empty] | 1 | [8 empty] | 1 | 1 |  | 1 |  |  |  |  | 1 |  |  |  | 1
Miramar | N | 13180 | EVOC Driving Course
Miramar | S | 13210 | Hourglass Park Field House | [9 empty] | 1 | 1
Miramar | N | 13220 | Student Services Center (Interim Library) | [9 empty] | 1 | 1 |  | 1 |  |  | 1 |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  | 1 |  | 1
Miramar | S | 13230 | Computing & Distribution Center & HVAC Upgrade | [10 empty] | 1 | [19 empty] | 1
Miramar | N | 13240 | Cafeteria/Bookstore & Student/Campus Center | [9 empty] | 1 |  |  | 1 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 1
Miramar | S | 13250 | Cogeneration Facility | [10 empty] | 1
Miramar | N | 13310 | Science Building - Renovate Classrooms to Labs/Add Wing | [8 empty] | 1 | 1 | 1 |  | 1 |  |  | 1 | 1 |  | 1 |  | 1 | [5 empty] | 1 |  |  |  | 1 |  | 1
Miramar | S; N | 13410 | Automotive Technology Career Instructional Building | [9 empty] | 1 | 1 | 1
Miramar | N | 13420 | Aviation Maintenance Technology Center | [8 empty] | 1 | 1 | 1 | 1 | [6 empty] | 1 | 1 |  | 1 |  |  |  | 1 | 1 | 1 |  | 1 | 1
Miramar | N | 13430 | Heavy Duty Advanced Transportation Technology Center | [9 empty] | 1 | [6 empty] | 1 |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 1
Miramar | S | 13511
Miramar | S | 13520 | Construct "Leave a Legacy Plaza"
Miramar | S | 13530 | Boiler Expansion
Miramar | N | 13540 | Parking Structure #1 & Police/Emergency Center | [9 empty] | 1 | 1 |  |  |  |  | 1 |  |  | 1 | [7 empty] | 1 |  |  |  | 1 |  | 1
Miramar | N | 13550 | Campus Safety Enhancements
Miramar |  | 13560 | [10 empty] | 1 | [16 empty] | 1
Miramar |  | 13561 | [9 empty] | 1 | 1 | 1 |  | 1 | [13 empty] | 1 |  |  | 1 | 1
Miramar |  | 13562 | [10 empty] | 1
Miramar |  | 13563 | [10 empty] | 1
Miramar | S | 13610 | Arts Village
Miramar | S | 13620 | Reprographic/Mailroom Relocation
Miramar | N | 13630 | College Service Center | [9 empty] | 1 | [8 empty] | 1 | [7 empty] | 1 |  |  |  | 1
Miramar | N | 13650 | Expansion of Maintenance Facilities | [9 empty] | 1 | [8 empty] | 1 |  |  | 1 |  |  |  |  | 1
Miramar | N | 13670 | Administration Building | [9 empty] | 1 | 1 |  |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  | 1
Miramar | N | 13680 | Remodel A-100 Building (CE Classrooms) |  |  |  |  | 1 |  |  |  |  | 1 | [5 empty] | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  | 1 | 1
Miramar |  | SITE | [9 empty] | 1 | 1 | 1 |  | 1 |  |  | 1 |  | 1 | 1 |  |  | 1 |  |  |  | 1 | 1 | 1 |  | 1 | 1 |  | 1
CE | N | 13690 | Fire Science and EMT Training Facility | [9 empty] | 1 | [8 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
CE | S | 14110 | ECC - Land Acquisition & Relocation Skills Center
CE | N | 14120 | Clairemont/Linda Vista - Land Acquisition & Building (Land $1.8M) | [12 empty] | 1 | [5 empty] | 1 | [10 empty] | 1
CE | S | 14210 | North City Campus (Land $22M) | [10 empty] | 1 | [6 empty] | 1 | 1 | 1 |  | 1 | [5 empty] | 1
CE | S | 14215 | North City Parking Structure | [15 empty] | 1 | [14 empty] | 1 |  | 1
CE | N | 14220 | Educational Cultural Complex - Phase IIB Wing | [11 empty] | 1 | [7 empty] | 1 |  | 1 |  |  |  |  | 1
CE | S | 14310 | West City Campus | [8 empty] | 1 |  | 1 |  |  |  |  | 1 |  |  | 1 |  |  | 1 | [8 empty] | 1
CE | S | 14420 | Consolidation of Centre City & Cesar Chavez Campus (Land $5.7M) | [8 empty] | 1 | 1 | [11 empty] | 1 |  |  |  | 1 |  |  |  |  | 1
CE | S | 14425 | Cesar Chavez Campus Parking Structure | [9 empty] | 1 | [7 empty] | 1 | 1 | [7 empty] | 1 |  |  |  | 1
CE | S | 14520 | Seismic Retrofit Secondary Effects @ Centre City Skills Center
CE | S | 14610 | Mid-City Campus (Land $0.5M)
CE | S | 14710 | Land Acquisition/Renovation of Building @DSC (Land $5.4M)
CE |  | SITE | [11 empty] | 1 |  | 1 | [5 empty] | 1
|  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 8 | 43 | 30 | 5 | 24 | 0 | 1 | 19 | 8 | 6 | 38 | 8 | 4 | 25 | 0 | 0 | 0 | 6 | 35 | 6 | 1 | 14 | 39 | 0 | 18 | 0

## Old-11110
Project # | Campus | Building | Fusion # | Floor | Trade per CSI | Contractor | Description | Make | Model | Contract | O&M | O&M Binder # | As-Built | As-Built Archive # | Submittals | Warranty | Warranty Start | Warranty Duration | Warranty Expires | Fixed-Asset Tag | FA Tag #
11110 |  |  |  |  | 24-HVAC |  |  |  |  | Yes | Yes |  |  |  |  | Yes |  |  |  | No
[11 empty] | No |  |  |  |  | No
[11 empty] | No, but close enough |  |  |  |  | No, but close enough
[11 empty] | N/A |  |  |  |  | N/A
[11 empty] | ? |  |  |  |  | ?
[11 empty] | Yes |  |  |  |  | Yes
[11 empty] | Yes |  |  |  |  | Yes
[11 empty] | No |  |  |  |  | No
[11 empty] | No |  |  |  |  | No

## Old-Program
P | Campus | Project Description | Proj # | DSA # | DSA Cert? | LEED Cert Target | LEED | LEED Cert Received Year | LEED Documentation Letter/Plaque Up? | Photos in SP | # Photos in SP | GIS Updated | Minutes | Minutes CM13 vs SP | Soils Report | Record Dwg | BIM | Commissioning Report Located | Labor Warranties Filed / Logged? | Equip O&M's and Warranties Filed / Logged? | Hard-Copy O&M / Warranty Locations | Record BIM Model Received? | Record As-Builts Doc's Logged (w/ specs) | Hard-Copy Record/As-Built Location | COBiE Info Captured? | CM13 Contracts in SharePoint | CM13 CO's in SharePoint | CO's + CCD's in SharePoint | Evidence of Scope Changes to DSA | Minutes in SharePoint (move from CM13??) | Photos in SharePoint | Have Items Been transferred to Facilities EDMS | IOR (and DSABox) records in SP | All NOC's in SP (and final releases?) | Financial Close-out? | Lessons Learned? | Maint info ID'd (ie Perm BMPs, SF) | Incorporated into Campus Security Plan | RFIs (move from CM13 to SP?) | Submittals? | Comments | Project Budget |  | Construction Complete? | Date Construction Complete |  | S - Ballot Reference # | N - Ballot Reference # | On Both Ballots
S | City | "L" Building Renovation | 11410 | N/A | N/A | [20 empty] | 84% | [15 empty] | $ 9,485,942 | 1 | Yes | Apr-09 A | 1 | S.IV.1 | N/A
S | City | "P" Building Renovation | 11420 | N/A | N/A | Certified | Yes | 2012-08-01 | [33 empty] | $ 10,576,526 | 1 | Yes | Dec-09 A | 1 | S.IV.1 | N/A
S | City | "R" Building Renovation | 11710 | N/A | N/A | Silver | Yes | 2008-04-01 | [33 empty] | $ 3,388,698 | 1 | Yes | Aug-07 A | 1 | N/A | N/A |  | 1
S | City | Career Technology Center | 11220 | 04-108850 | Yes | Gold | Yes | 2011-01-01 | [12 empty] | City 6, 7, 8, 9, 10, 11 |  |  | City-019; 021; 026-027; 030; 034; 049-050; 057; 059; 096 |  | 75% | 83% | [14 empty] | $ 63,313,503 | 1 | Yes | Apr-10 A | 1 | S.III.2 | N/A
S | City | Land Acquisition (Career Technology Parcel Land $24.M) | 11140 | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  |  |  | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | $ 24,745,904 |  | N/A | N/A |  | N/A | N/A |  | 1
S | City | Land Acquisition + General Purpose Classroom Building (Land $21.8M) | 11810 | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  |  |  | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | $ 80,363,499 |  | Yes | Aug-12 A |  | N/A | N/A |  | 1
S | City | Modular Village | 11720 | N/A | N/A | [36 empty] | $ 1,446,217 | 1 | Yes | Jan-08 A | 1 | N/A | N/A |  | 1
S | Mesa | Allied Health Building, Parking and Roadwork | 12130 | N/A | N/A | Gold | Yes | 2010-08-01 | [33 empty] | $ 26,869,668 | 1 | Yes | Aug-09 A | 1 | S.I.3 | N/A
S | Mesa | Cogeneration Facility | 12450 | 04-106354 | Yes | [20 empty] | 0% | [15 empty] | $ 3,696,342 | 1 | Yes | Jan-05 A | 1 | S.IV.5 | N/A
S | Mesa | East Campus Improvement Project and Police Station | 12210 | 04-108059; 04-108072; 04-108993; 04-110263 | Yes | Gold | Yes | 2010-02-01 | [12 empty] | Mesa: 27 |  |  | Mesa-065 |  | 47% | [15 empty] | $ 34,963,741 | 1 | Yes | Jan-10 A | 1 | S.II | N/A
S | Mesa | Humanities, Languages & Multicultural Studies Building | 12320 | 04-101936 | No | [15 empty] | Mesa: 29 | [20 empty] | $ 53,175 | 1 | Yes | Feb-03 A | 1 | S.III.2 | N/A
S | Mesa | Muir Property Acquisition (Land $12.7M) | 12510 | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  |  |  | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | $ 17,139,697 |  | N/A | N/A |  | N/A | N/A |  | 1
S | Mesa | Renovate Visual Arts Program | 12250 | 04-108114 | Yes | [20 empty] | No |  | A | A | No | No |  | No | No | [7 empty] | $ 1,518,626 | 1 | Yes | Sep-07 A | 1 | S.II.5 | N/A
S | Mesa | Social Behavioral Science | 12721; 12723 | 04-112394 | Yes | Silver | Yes | 2015-05-01 | [12 empty] | Mesa: 26 |  |  | Mesa-090-092 | [17 empty] | $ 40,515,000 | 1 | Yes | Aug-14 A | 1 | S.III.1 | N/A
S | Mesa | Student Services Facility | 12410 | 04-110328 ? | N/A | Gold | Yes | 2012-12-01 | [15 empty] | Mesa - 046; 050--062; 068-073; 094; 097 | [17 empty] | $ 44,939,067 | 1 | Yes | Oct-12 A | 1 | S.IV | N/A
S | Miramar | Arts & Humanities Building - Design | 13150 | 04-109543 | Yes | Silver | Yes | 2011-07-01 | [12 empty] | Miramar: 10 | [20 empty] | $ 768,040 |  | N/A | N/A |  | S.IV.2 | N/A
S | Miramar | Arts Village | 13610 | 04-107973 | Void | [36 empty] | $ 465,392 | 1 | Yes | Jul-06 A | 1 | N/A | N/A |  | 1
S | Miramar | Automotive Technology Career Instructional Building | 13410 | 04-109997 | Yes | Gold | Yes | 2012-04-01 | [12 empty] | Miramar: 19 | [20 empty] | $ 1,893,176 | 1 | Yes | Mar-05 A | 1 | S.I.3 | N/A
S | Miramar | Boiler Expansion | 13530 | N/A | N/A | [36 empty] | $ 2,271,840 | 1 | Yes | Mar-06 A | 1 | N/A | N/A |  | 1
S | Miramar | Cogeneration Facility | 13250 | N/A | N/A | [36 empty] | $ 3,566,965 | 1 | Yes | Nov-08 A | 1 | S.II.5 | N/A
S | Miramar | Computing & Distribution Center & HVAC Upgrade | 13230 | 04-104134 | No | [15 empty] | Miramar: 27, 28, 32, 33 |  |  | Miramar-053; 058 | [17 empty] | $ 7,672,189 | 1 | Yes | Jul-05 A | 1 | S.II.3 | N/A
S | Miramar | Construct "Leave a Legacy Plaza" | 13520 | N/A | N/A | [36 empty] | $ 1,311,165 | 1 | Yes | Aug-07 A | 1 | N/A | N/A |  | 1
S | Miramar | Hourglass Park Field House | 13210 | 04-107167 | No | Certified | Yes | 2009-12-01 | [12 empty] | Miramar: 20, 31 |  |  | Miramar-026; 054 | [17 empty] | $ 22,283,662 | 1 | Yes | Mar-09 A | 1 | S.II.1 | N/A
S | Miramar | Infrastructure - Phase I | 13511; 13514 | 04-108929 | Yes | [36 empty] | $ 11,120,157 | 1 | Yes | May-10 A | 1 | N/A | N/A | x | 1
S | Miramar | Library/Learning Resource Center - Design | 13110; 13111 | 04-109960 | Yes | Certified | Yes | 2015-05-01 | [33 empty] | $ 2,653,044 |  | N/A | N/A |  | S.I.1 | N/A
S | Miramar | Reprographic/Mailroom Relocation | 13620 | N/A | N/A | [36 empty] | $ 1,120,915 | 1 | Yes | Mar-09 A | 1 | N/A | N/A |  | 1
S | Miramar | Science & Technology Building | 13120 | N/A | N/A | [36 empty] | $ 9,025,573 | 1 | Yes | Feb-05 A | 1 | S.I.2 | N/A
S | Miramar | Technology Building - Design | 13135 | N/A | N/A | [36 empty] | $ 760,871 |  | N/A | N/A |  | S.I.4 | N/A
S | CE | ECC - Land Acquisition & Relocation Skills Center | 14110 | 04-107912 | No | Gold | Yes | 2010-07-01 | [6 empty] | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | CE-004 | N/A | N/A |  | 95% |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | $ 31,731,930 | 1 | Yes | Aug-09 A | 1 | S.I.1 | N/A
S | CE | Land Acquisition/Renovation of Building @DSC (Land $5.4M) | 14710 | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  |  |  | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | $ 7,937,788 |  | Yes | Mar-10 A |  | S.VII | N/A
S | CE | Mid-City Campus (Land $0.5M) | 14610 | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  |  |  | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0 |  | Yes | Feb-01 A |  | S.VI | N/A
S | CE | North City Campus (Land $22M) | 14210 | N/A | N/A | Gold | Yes | 2014-11-01 |  | N/A | N/A |  |  |  | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | $ 43,432,099 |  | Yes | Aug-13 A |  | S.II.1 | N/A
S | CE | North City Parking Structure | 14215 | N/A | N/A | N/A for Parking Structure |  | N/A for Parking Structure | N/A for Parking Structure | [17 empty] | 1 DB contract | 100% | [13 empty] | $ 5,185,821 | 1 | Yes | Dec-11 A | 1 | N/A | N/A |  | 1
S | CE | Seismic Retrofit Secondary Effects @ Centre City Skills Center | 14520 | 04-103471 | No | N/A |  | N/A | [33 empty] | $ 1,551,919 | 1 | Yes | Jan-06 A | 1 | S.V.2 | N/A
S | CE | West City Campus | 14310 | 04-107524; 04-113290 | Yes | Gold | Yes | 2010-05-01 | [12 empty] | CE - 2, 3, 4, 5, 6, 7, 11 | [20 empty] | $ 18,199,031 | 1 | Yes | May-09 A | 1 | S.III.1 | N/A
S | District | COP Expenditures | 15120 | N/A | N/A | N/A |  | N/A | [6 empty] | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | $ 27,761,548 |  | Yes | Aug-07 A |  | N/A | N/A |  | 1
S | Mesa | Fitness Center | 12722 | 04-112980 | No | [36 empty] | $ 15,279,000 | 1 | Construction | Dec-15 |  | S.IV | N/A
S | CE | Cesar Chavez Campus Parking Structure | 14425 | 04-112885 | Yes | N/A for Parking Structure |  | N/A for Parking Structure | N/A for Parking Structure | [9 empty] | B | B |  | Get Access | Get Access | CE-008 |  |  |  | 2015-11-12 | [13 empty] | $ 7,974,889 | 1 | Yes | May-15 A | 1 | N/A | N/A |  | 1
S | CE | Consolidation of Centre City & Cesar Chavez Campus (Land $5.7M) | 14410; 14420 | 04-111289 | Yes | Silver | [17 empty] | CE-012; 014-016; 018-020 | [17 empty] | $ 50,037,320 | 1 | Yes | Jul-15 A | 1 | S.IV.1 | N/A
S | District | Computer Hardware & Software | 14810 | N/A | N/A | N/A |  | N/A | [6 empty] | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | $ 37,613,379 |  | N/A | N/A |  | S.VIII | N/A
S | District | Prop S Program Management | 15110 | N/A | N/A | N/A |  | N/A | [6 empty] | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | $ 28,324,247 |  | N/A | N/A |  | N/A | N/A |  | 1
S | Mesa | Campus Facilities Support Areas | 12220 | N/A | N/A | [36 empty] | $ 4,168,253 | 1 | Design/Bid | Nov-16 |  | S.II.5 | N/A
S | City | Child Development Center | 11210 | N/A | N/A | [36 empty] | $ 11,023,185 | 1 | Future | Aug-19 |  | S.II.1 | N/A
S | Reserve | Proposition S Reserve | 15130 | N/A | N/A | N/A |  | N/A | [6 empty] | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | $ 2,057,299 |  | N/A | N/A |  | N/A | N/A |  | 1
N | City | "M" Classroom Building | 11310 | 04-112843 | Yes | Silver | Yes | 2015-03-01 | [12 empty] | City: 21, 22, 23, 24, 26 |  |  | City-015-016 |  | Yes |  | reqest to TF 6/17/2015 |  | Yes | 88 |  | No | [8 empty] | $ 9,594,000 | 1 | Yes | Nov-14 A | 1 | S.IV.1 | N.III.3 | x
N | City | Humanities Building | 11110 | 04-110503 | Yes | Gold | [17 empty] | City: 008-011; 088; 094-095; 097 |  | 75% | [15 empty] | $ 92,478,598 | 1 | Yes | Apr-14 A | 1 | S.I.2 | N.II.1 | x
N | City | Science Building | 11260 | 04-111042 | No | Silver | [17 empty] | City-062; 087; 089-090 | [17 empty] | $ 57,408,094 | 1 | Yes | Aug-13 A | 1 | S.IV (?) | N.I.1 | x
N | Mesa | Design Center Renovation (Temporary Technology Village) | 12550 | 04-110670 | Yes | [15 empty] | Mesa: 3 | [20 empty] | $ 5,307,273 | 1 | Yes | Oct-10 A | 1 | N/A | N/A |  | 1
N | Mesa | I-300 Building (Programming/Demolition) | 12600 | N/A | N/A | [36 empty] | $ 350,809 | 1 | Yes | Nov-14 A | 1 | N/A | N/A |  | 1
N | Mesa | LRC Language Labs | 12290 | 04-112665 | Yes | [18 empty] | Mesa-024; 030 | [17 empty] | $ 2,513,000 | 1 | Yes | Aug-13 A | 1 | N/A | N/A |  | 1
N | Mesa | Math and Science Building | 12111; 12110 | 04-111098 | Yes | Silver | Yes | 2014-11-01 | [12 empty] | Mesa: 8, 11, 12, 20, 21, 22, 23, 24 | [20 empty] | $ 106,307,816 | 1 | Yes | Aug-13 A | 1 | S.I.2 | N.I.1 | x
N | Mesa | Modular Village (Phase 1 & 2) | 12540 | N/A | N/A | [36 empty] | $ 2,779,115 | 1 | Yes | Oct-10 A | 1 | N/A | N/A |  | 1
N | Mesa | Temporary Parking/All Weather Track/Stadium Restroom | 12530; 12531; 12535 | 04-110315; 04-111790; 04-111971 | Yes | [15 empty] | Mesa: 19 |  |  | Mesa-031 | [17 empty] | $ 8,328,634 | 1 | Yes | Aug-12 A | 1 | N/A | N/A |  | 1
N | Miramar | Administration Building | 13670 | 04-112383 | Yes | Gold | Yes | 2015-12-01 | [33 empty] | $ 11,400,000 | 1 | Yes | Jul-14 A | 1 | N/A | N/A |  | 1
N | Miramar | Arts & Humanities Building & Technology Building | 13150; 13140 | 04-109543 | Yes | Silver | Yes | 2011-07-01 | [12 empty] | Miramar: 10 | [20 empty] | $ 31,276,362 | 1 | Yes | Nov-10 A | 1 | N/A | N/A |  | 1
N | Miramar | Aviation Maintenance Technology Center | 13420 | 04-111402 | Yes | Gold | Yes | 2013-03-01 | [33 empty] | $ 10,751,857 | 1 | Yes | Jun-12 A | 1 | S.IV.4 | N.III.1 | x
N | Miramar | Cafeteria/Bookstore & Student/Campus Center | 13240 | 04-111062 | No | Silver | [14 empty] | Miramar: 18 |  |  | Miramar-021; 024-025; 042-043; 045-052 | [17 empty] | $ 39,545,678 | 1 | Yes | Mar-13 A | 1 | N/A | N.IV.2
N | Miramar | College Service Center | 13630 | 04-11520 | Yes | Silver | [35 empty] | $ 5,938,078 | 1 | Yes | Jul-12 A | 1 | N/A | N/A |  | 1
N | Miramar | Expand Automotive Technology Career Instructional Building | 13410 | 04-109997 | Yes | [15 empty] | Miramar: 19 | [20 empty] | $ 3,493,719 | 1 | Yes | Mar-11 A | 1 | N/A | N.III.3
N | Miramar | Fire Science and EMT Training Facility | 13690 | 04-112341 | Yes | Silver | [17 empty] | Miramar-009 | [17 empty] | $ 16,333,000 | 1 | Yes | Jul-14 A | 1 | S.III.1 | N.I.1 | x
N | Miramar | Heavy Duty Advanced Transportation Technology Center | 13430 | 04-110830 | Yes | Silver | Yes | 2013-10-01 | [12 empty] | Miramar: 15 |  |  | Miramar-021; 024-025; 042-043; 045-052 | [17 empty] | $ 14,371,928 | 1 | Yes | May-13 A | 1 | N/A | N.III.2
N | Miramar | Library/Learning Resource Center | 13110; 13111 | 04-109960 | Yes | [36 empty] | $ 39,006,991 | 1 | Yes | Jun-12 A | 1 | N/A | N/A |  | 1
N | Miramar | Parking Structure #1 & Police/Emergency Center | 13540 | 04-110712 | Yes | Platinum | Yes | 2012-04-01 | [12 empty] | Miramar: 1, 6 |  |  | Miramar-016 | [17 empty] | $ 15,998,765 | 1 | Yes | Oct-11 A | 1 | N/A | N.IV.3; N.IV.5
N | Miramar | Science Building - Renovate Classrooms to Labs/Add Wing | 13310 | 04-112513 | Yes | Silver | Yes | 2015-05-01 | [33 empty] | $ 34,418,186 | 1 | Yes | Mar-15 A | 1 | N/A | N.II.1
N | Miramar | Student Services Center (Interim Library) | 13220 | 04-112314 | Yes | Silver | Yes | 2015-02-01 | [15 empty] | Miramar-006; 055 | [17 empty] | $ 8,050,970 | 1 | Yes | Jun-14 A | 1 | S.IV.3 | N.IV.1 | x
N | CE | Clairemont/Linda Vista - Land Acquisition & Building (Land $1.8M) | 14120 | N/A | N/A | Silver | Yes | 2013-01-01 | [33 empty] | $ 22,396,070 |  | Yes | Oct-12 A |  | N/A | N.I.1
N | CE | Educational Cultural Complex - Phase IIB Wing | 14220 | 04-111330 | Yes | Silver | Yes | 2014-11-01 | [12 empty] | CE: 8, 9 |  |  | CE-012; 014-015 | [17 empty] | $ 18,686,945 | 1 | Yes | Aug-13 A | 1 | N/A | N.II.1
N | City | Language/Speech/Visual Arts ("C" Building) | 11340 | 04-112710 | No | Silver | [17 empty] | City-063-067; 083 | [17 empty] | $ 21,128,910 | 1 | Construction | Oct-15 |  | S.V | N.III.2 | x
N | Mesa | Cafeteria and Bookstore / Stockroom | 12420 | 04-112803 | No | [36 empty] | $ 44,347,083 | 1 | Construction | Jan-16 |  | N/A | N.II.2
N | City | Infrastructure - Central Plant/Sewer & Storm Drain/Data & IT Projects | 11430 | 04-110878; 04-111010; 04-111216 | Yes | [15 empty] | City: 2, 28 |  |  | City-022 | [17 empty] | $ 19,542,870 | 1 | Ongoing | Feb-12 A | 1 | S.VI | N.IV.1 | x
N | Mesa | Infrastructure - Fire Lane/Central Plant/IT | 123*** | 04-112591; 04-112720; 04-113173 | No | [36 empty] | $ 21,568,549 | 1 | Ongoing | Oct-18 |  | N/A | N.III
N | Miramar | Campus Safety Enhancements | 13550 | N/A | N/A | [36 empty] | $ 446,356 | 1 | Yes | Jun-15 A | 1 | N/A | N.IV.6
N | Miramar | Infrastructure - Phase II | 135** | N/A | N/A | [36 empty] | $ 42,843,305 | 1 | Ongoing | Jul-18 |  | N/A | N.V.1 | x
N | District | Prop N Program Management | 15210 | N/A | N/A | N/A |  | N/A |  | N/A | N/A |  |  |  | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | $ 51,027,440 |  | N/A | N/A |  | N/A
N | City | "A" Building Renovation | 11330 | N/A | N/A | combined-adt | [35 empty] | $ 24,605,847 | 1 | Design/Bid | Jul-18 |  | S.IV.1 | N.III.1 | x
N | City | "D" Building Roof | 11320 | N/A | N/A | combined-adt | [35 empty] | $ 4,817,050 | 0 | Design/Bid | Jul-18 |  | S.VI | N.III.4 | x
N | City | Engineering Technology Building ("T" Building) | 11250 | ? 04-100128 | No | combined-adt | [35 empty] | $ 34,722,953 | 0 | Design/Bid | Jul-18 |  | S.I.1 | N.I.2 | x
N | Mesa | Center for Business and Technology | 12120 | N/A | N/A | [36 empty] | $ 32,394,394 | 1 | Design/Bid | Oct-17 |  | N/A | N.I.2
N | Mesa | Fine Arts and Dramatic Arts | 12520 | N/A | N/A | [36 empty] | $ 14,569,538 | 1 | Design/Bid | May-18 |  | N/A | N.I.3
N | Miramar | Expansion of Maintenance Facilities | 13650 | N/A | N/A | NOT LEED |  | NOT LEED | [33 empty] | $ 3,621,536 | 1 | Construction | Jul-16 |  | N/A | N.IV.4
N | Miramar | Remodel A-100 Building (CE Classrooms) | 13680 | 04-113249 | No | Certified | [35 empty] | $ 6,600,000 | 1 | Design/Bid | Jan-17 |  | N/A | N/A |  | 1
N | Miramar | Remodel Existing Police Academy (A-200 Building) | 13170 | 04-113165 | No | [36 empty] | $ 6,200,000 | 1 | Construction | Mar-16 |  | N/A | N/A |  | 1
N | City | Business Technology Building | 11240 | 04-110503 | Yes | Gold | [17 empty] | City: 008-011; 088; 094-095; 097 | [17 empty] | $ 2,151,675 | 1 | Yes | Apr-14 A | 1 | S.I.3 | N.I.3 | x
N | Miramar | EVOC Driving Course | 13180 | N/A | N/A | [36 empty] | $ 5,000,000 | 1 | Future | May-18 |  | N/A | N.I.2
N | Reserve | Proposition N Reserve | 15220 | N/A | N/A | N/A | [8 empty] | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | $ 12,611,667 |  | Reserve | N/A |  | N/A | N/A

## Old-LEED BAckup
COLLEGE | PROJECT | POINTS | LEVEL | USGBC | COMMENTS | CERT | Scorecard
CE | ECC Skills Center (Skills Cen ter for Education & Technology) | 39/69 | Gold | 2.1 | LEED Gold certified | 2010-07-01 | http://www.usgbc.org/projects/skills-center-education-technology
CE | West City Campus (West City Center) | 39/69 | Gold | 2.1 | LEED Gold certified | 2010-05-01 | http://www.usgbc.org/projects/west-city-center
CE | Cesar Chavez Campus (Cesar Chavez Educational Center) | Tracking 34 as of 2/24/10 | Silver | 2.2 | Certification in progress (2/25/2016) |  | http://www.usgbc.org/projects/cesar-chavez-educational-center | http://portal.sdccdprops-n.com/ce/ccc/Project%20Files/C%20Design%20Information/03%20Construction%20Documents/14420_LEEDScorecard_20100224.pdf
CE | Continuing Education Mesa College Campus (Linda Vista Center) | 51/110 | Silver | V3 2009 | LEED Silver certified | 2013-01-01 | http://www.usgbc.org/projects/linda-vista-center
CE | ECC Expansion (Educational Cultural Complex Expansion) | 56/110 | Silver | V3 2009 | LEED Silver certified | 2014-11-01 | http://www.usgbc.org/projects/educational-cultural-complex-expansion
CE | North City Campus | 42/69 | Gold | 2.2 | LEED Gold certified | 2014-11-01 | http://www.usgbc.org/projects/sdccd-north-city
-
City | Science Building | Tracking 37 as of 2/16/2010 | Silver | 2.2 | Certification in progress (2/25/2016) |  | http://www.usgbc.org/projects/san-diego-city-college-science-building | http://portal.sdccdprops-n.com/city/sciencebuild/Project%20Files/C%20Design%20Information/02%20Preliminary%20Design/11260_Science%20LEED%20Scorecard_2010.02.16.xls
City | Arts & Humanities | Tracking 46 as of 11/21/2008 | Gold | 2.2 | Certification in progress (2/25/2016) |  | http://www.usgbc.org/projects/san-diego-city-college-bahq | http://portal.sdccdprops-n.com/city/Human/Project%20Files/C%20Design%20Information/02%20Preliminary%20Design/11110_LEED_ProjectChecklist_Gold_2008.11.20.pdf
City | Business Technology | Combined with AH | Gold | 2.2 | Certification in progress (2/25/2016) |  | http://www.usgbc.org/projects/san-diego-city-college-bahq
City | Math and Social Sciences (SD-CityCollege Math&Social Sci. & Garage) | 35/69 | Silver | 2.2 | LEED Silver certified | 2015-07-01 | http://www.usgbc.org/projects/sd-citycollege-mathsocial-sci-garage
City | Career Technology Center (Vocation Technology Center | 40/69 | Gold | 2.2 | LEED Gold certified | 2011-01-01 | http://www.usgbc.org/projects/vocation-technology-center-city-college
City | R Building (Learning Resource Center Renovation) | 27/57 | Silver | 2 | LEED Silver certified | 2008-04-01 | http://www.usgbc.org/projects/learning-resource-center-renovation
City | P Building | 27/69 | Certified | 2.2 | LEED certified | 2012-08-01 | http://www.usgbc.org/projects/san-diego-city-college-p-building
City | C Building | Tracking 55-65 as of 12/31/2015 | Silver | V3 2009 | Certification in progress (2/25/2016) |  | http://www.usgbc.org/projects/sdccd-c-building-remodel
City | M Building | 55/110 | Silver | V3 2009 | LEED Silver certified | 2015-03-01 | http://www.usgbc.org/projects/m-building-city-college
City | A Building (City College Renovation of BLDG A) | Tracking 61 as of 2/25/2016 | Silver | V3 2009 | Certification in progress (2/25/2016) |  | http://www.usgbc.org/projects/city-college-renovation-bldg
City | T Building (City College Renovation of BLDG T) | Tracking 60 as of 2/25/2016 | Silver | V3 2009 | Certification in progress (2/25/2016) |  | http://www.usgbc.org/projects/city-college-renovation-bldg-t
City | Child Development Center |  | Silver | TBD
-
Mesa | Allied Health | 39/69 | Gold | 2.2 | LEED Gold certified | 2010-08-01 | http://www.usgbc.org/projects/mesa-college-allied-health-building
Mesa | Police Station (Police Offices) | 43/69 | Gold | 2.2 | LEED Gold certified | 2010-02-01 | http://www.usgbc.org/projects/mesa-college-police-offices
Mesa | Social Behavioral Sciences Building (SBSB) | 51/110 | Silver | V3 2009 | LEED Silver certified | 2015-05-01 | http://www.usgbc.org/projects/mesa-college-sbsb
Mesa | Student Services | 41/69 | Gold | 2.2 | LEED Gold certified | 2012-12-01 | http://www.usgbc.org/projects/mesa-college-student-services
Mesa | Math+Science Complex | 34 | Silver | 2.2 | LEED Silver certified | 2014-11-01 | No link available - using PDF of scanned letter on website
Mesa | Center for Business Technology | 50 | Silver | V3 2009 | Certification in progress (2/25/2016) |  | http://www.usgbc.org/projects/mesa-center-business-technology
Mesa | Exercise Science Center (Fitness Center) | Tracking 54 as of 6/20/2013 | Silver | V3 2009 | Certification in progress (2/25/2016) |  | http://www.usgbc.org/projects/san-diego-mesa-college-fitness-center | http://portal.sdccdprops-n.com/mesa/12722/Project%20Files/D%20Design%20Review/LEED%20Presentation_2013-06-20.pdf
Mesa | Cafeteria/Bookstore & Stockroom (CCAB) - TBK Mesa Commons | 55 | Silver | V3 2009 | Certification in progress (2/25/2016) |  | http://www.usgbc.org/projects/mesa-college-ccab-building
Mesa | Fine Arts & Dramatic Arts | 50 | Silver | V3 2009 | Awaiting completion of design
- | Mesa College Design Center | None
- | Facilities Services Remodel | Not LEED
-
Miramar | Police Station (Police Substation) | 53/69 | Platinum | 2.2 | LEED Platinum certified | 2012-04-01 | http://www.usgbc.org/projects/miramar-college-police-substation
Miramar | Heavy Duty Adv. Transp. Tech. Center | 33/69 | Silver | 2.2 | LEED Silver certified | 2013-10-01 | http://www.usgbc.org/projects/miramar-heavy-duty-transportation
Miramar | Aviation Maintenance Tech Center | 40/69 | Gold | 2.2 | LEED Gold certified | 2013-03-01 | http://www.usgbc.org/projects/miramar-college-aviation-building
Miramar | Caf/Bookstore + Student/Campus Center ( | 39 | Silver | 2.2 | Certification in progress (2/25/2016) |  | http://www.usgbc.org/projects/miramar-college-student-union
Miramar | Student Service Center | 52/110 | Silver | V3 2009 | LEED Silver certification | 2015-02-01 | http://www.usgbc.org/projects/miramar-college-student-service-center
Miramar | College Services Center | 70 | Silver | 3 | Certification in progress (2/25/2016) |  | http://www.usgbc.org/projects/college-services-center-miramar-college
Miramar | Library Learning Resource Center | 28/69 | Certified | 2.2 | LEED certified | 2015-05-01 | http://www.usgbc.org/projects/miramar-college-llrc
Miramar | Hourglass Park Field House | 26 | Certified | 2.2 | LEED certified | 2009-12-01 | No link available - using PDF of scanned letter on website
Miramar | Humanities & Arts Building (Miramar Arts & Humanities) | 35/69 | Silver | 2.2 | LEED Silver certified | 2011-07-01 | http://www.usgbc.org/projects/sdccd-miramar-arts-humanities
Miramar | Mathematics & Business Building (Miramar Technology Building) | 35/69 | Silver | 2.2 | LEED Silver certified | 2011-07-01 | http://www.usgbc.org/projects/sdccd-miramar-technology-building
MIramar | Automotive Technology Center Expansion | 40/69 | Gold | 2.2 | LEED Gold certified | 2012-04-01 | http://www.usgbc.org/projects/miramar-college-auto-tech-career-buildin
MIramar | New Administration Building | 60/110 | Gold | V2009 | LEED Gold certified | 2015-12-01 | http://www.usgbc.org/projects/miramar-college-administration-building
Miramar | A-100 Remodel | 48 | Certified | V3 2009 | Certification in progress (2/25/2016) |  | http://www.usgbc.org/projects/miramar-college-100-remodel
Miramar | A-200 Remodel (E-100 Replacement) | None |  |  | Not attempting LEED Certification
Miramar | Fire/Science EMT |  | Silver | V3 2009 | Certification in progress (2/25/2016) |  | http://www.usgbc.org/projects/miramar-fire-emt-0
Miramar | Renovate Science Building | 53/110 | Silver | V3 2009 | LEED Silver certified | 2015-05-01 | http://www.usgbc.org/projects/sdccd-miramar-technology-building
- | Facilities Maintenance expansion? | None | Not LEED
Platinum - 1
Gold - 12
Silver - 25
Certified - 4
Total = 42

## Old-Progress Graphs
| SDCCD / Dow |  |  | Projections
|  | Start | Today | FY 15-16 |  |  |  | FY 16-17
|  | 2016-01-01 | 2020-07-22 | 2016-06-30 | 2016-09-30 | 2016-12-31 | 2017-03-31 | 2017-06-30
9A | #REF! | 21 | #REF! | 30 | 35 | 40 | 45 | 53
11A | #REF! | 3 | #REF! | 5 | 15 | 30 | 40 | 53
13 | #REF! | 1 | #REF! | 5 | 15 | 30 | 40 | 53
13A | #REF! | 1 | #REF! | 5 | 15 | 30 | 40 | 53
14 | #REF! | 3 | #REF! | 5 | 15 | 30 | 40 | 53
15 | #REF! | 0 | #REF! | 5 | 15 | 30 | 40 | 53
16 | #REF! | 0 | #REF! | 5 | 15 | 30 | 40 | 53
17 | #REF! | 0 | #REF! | 5 | 15 | 30 | 40 | 53
| #REF! | 67 | #REF!
| #REF! | 53 | #REF!

## Old-08-Warranties
Numbering Based on Based on 8/31/2015 Rainbow Report | [6 empty] | 2020-07-22 | 3 | i.e. - HVAC - Mechanical | [6 empty] | i.e. Electrical
# | P | SDCCD # | S - Ballot Reference # | N - Ballot Reference # | DSA # | Campus | Project Description | Warranties Filed / Logged? | Warrantying Company | Warranty Start | Warranty Period | Warranty End | Hardcopy Location | Digital Location | Documentation Score | Warrantying Company | Warranty Start | Warranty Period | Warranty End | Hardcopy Location | Digital Location | Documentation Score | Comments
1 | S | 11410 | S.IV.1 | - | - | City | "L" Building Renovation
2 | S | 11420 | S.IV.1 | - | - | City | "P" Building Renovation
3 | S | 11710 |  | - | - | City | "R" Building Renovation
4 | S | 11220 | S.III.2 | - | 04-108850 | City | Career Technology Center
5 | S | 11140 |  | - | N/A | City | Land Acquisition (Career Technology Parcel Land $24.M) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | S | ? -- 11810 |  | - | N/A | City | Land Acquisition + General Purpose Classroom Building (Land $21.8M) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 | S | 11720 |  | - | - | City | Modular Village
8 | S | 12130 | S.I.3 | - | - | Mesa | Allied Health Building, Parking and Roadwork
9 | S | 12450 | S.IV.5 | - | 04-106354 | Mesa | Cogeneration Facility
10 | S | 12210 | S.II | - | 04-108059; 04-108072; 04-108993; 04-110263 | Mesa | East Campus Improvement Project and Police Station
11 | S | 12320 | S.III.2 | - | 04-101936 | Mesa | Humanities, Languages & Multicultural Studies Building
12 | S | 12510 |  | - | N/A | Mesa | Muir Property Acquisition (Land $12.7M) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | S | 12250 | S.II.5 | - | 04-108114 | Mesa | Renovate Visual Arts Program
14 | S | 12721; 12723 | S.III.1 | - | 04-112394 | Mesa | Social Behavioral Science
15 | S | 12410 | S.IV | - | - | Mesa | Student Services Facility
16 | S | 13150 | S.IV.2 | - | 04-109543 | Miramar | Arts & Humanities Building - Design
17 | S | 13610 |  | - | 04-107973 | Miramar | Arts Village
18 | S | 13410 | S.I.3 | - | 04-109997 | Miramar | Automotive Technology Career Instructional Building
19 | S | 13530 |  | - | - | Miramar | Boiler Expansion
20 | S | 13250 | S.II.5 | - | - | Miramar | Cogeneration Facility
21 | S | 13230 | S.II.3 | - | 04-104134 | Miramar | Computing & Distribution Center & HVAC Upgrade
22 | S | 13520 |  | - | - | Miramar | Construct "Leave a Legacy Plaza"
23 | S | 13210 | S.II.1 | - | 04-107167 | Miramar | Hourglass Park Field House
24 | S | 13511; 13514 |  | - | 04-108929 | Miramar | Infrastructure - Phase I
25 | S | 13110; 13111 | S.I.1 | - | 04-109960 | Miramar | Library/Learning Resource Center - Design
26 | S | 13620 |  | - | - | Miramar | Reprographic/Mailroom Relocation
27 | S | 13120 | S.I.2 | - | - | Miramar | Science & Technology Building
28 | S | 13135 | S.I.4 | - | - | Miramar | Technology Building - Design
29 | S | 14110 | S.I.1 | - | 04-107912 | CE | ECC - Land Acquisition & Relocation Skills Center | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
30 | S | 14710 | S.VII | - | N/A | CE | Land Acquisition/Renovation of Building @DSC (Land $5.4M) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
31 | S | 14610 | S.VI | - | N/A | CE | Mid-City Campus (Land $0.5M) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
32 | S | 14210 | S.II.1 | - | N/A | CE | North City Campus (Land $22M) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
33 | S | 14215 |  | - | - | CE | North City Parking Structure
34 | S | 14520 | S.V.2 | - | 04-103471 | CE | Seismic Retrofit Secondary Effects @ Centre City Skills Center
35 | S | 14310 | S.III.1 | - | 04-107524; 04-113290 | CE | West City Campus
36 | S | 15120 |  | - | N/A | District | COP Expenditures | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
37 | S | 12722 | S.IV | - | 04-112980 | Mesa | Fitness Center
38 | S | 14425 |  | - | 04-112885 | CE | Cesar Chavez Campus Parking Structure
39 | S | 14410; 14420 | S.IV.1 | - | 04-111289 | CE | Consolidation of Centre City & Cesar Chavez Campus (Land $5.7M)
40 | S | 14810 | S.VIII | - | N/A | District | Computer Hardware & Software | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
41 | S | 15110 |  | - | N/A | District | Prop S Program Management | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | S | 12220 | S.II.5 | - | - | Mesa | Campus Facilities Support Areas
43 | S | 11210 | S.II.1 | - | - | City | Child Development Center
44 | S | 15130 |  | - | N/A | Reserve | Proposition S Reserve | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
45 | N | 11310 | S.IV.1 | N.III.3 | 04-112843 | City | "M" Classroom Building
46 | N | 11110 | S.I.2 | N.II.1 | 04-110503 | City | Humanities Building
47 | N | 11260 | S.IV (?) | N.I.1 | 04-111042 | City | Science Building
48 | N | 12550 | - |  | 04-110670 | Mesa | Design Center Renovation (Temporary Technology Village)
49 | N | 12600 | - |  | - | Mesa | I-300 Building (Programming/Demolition)
50 | N | 12290 | - |  | 04-112665 | Mesa | LRC Language Labs
51 | N | 12111; 12110 | S.I.2 | N.I.1 | 04-111098 | Mesa | Math and Science Building
52 | N | 12540 | - |  | - | Mesa | Modular Village (Phase 1 & 2)
53 | N | 12530; 12531; 12535 | - |  | 04-110315; 04-111790; 04-111971 | Mesa | Temporary Parking/All Weather Track/Stadium Restroom
54 | N | 13670 | - |  | 04-112383 | Miramar | Administration Building
55 | N | 13150; 13140 | - |  | 04-109543 | Miramar | Arts & Humanities Building & Technology Building
56 | N | 13420 | S.IV.4 | N.III.1 | 04-111402 | Miramar | Aviation Maintenance Technology Center
57 | N | 13240 | - | N.IV.2 | 04-111062 | Miramar | Cafeteria/Bookstore & Student/Campus Center
58 | N | 13630 | - |  | 04-11520 | Miramar | College Service Center
59 | N | 13410 | - | N.III.3 | 04-109997 | Miramar | Expand Automotive Technology Career Instructional Building
60 | N | 13690 | S.III.1 | N.I.1 | 04-112341 | Miramar | Fire Science and EMT Training Facility
61 | N | 13430 | - | N.III.2 | 04-110830 | Miramar | Heavy Duty Advanced Transportation Technology Center
62 | N | 13110; 13111 | - |  | 04-109960 | Miramar | Library/Learning Resource Center
63 | N | 13540 | - | N.IV.3; N.IV.5 | ? - 04-111546 | Miramar | Parking Structure #1 & Police/Emergency Center
64 | N | 13310 | - | N.II.1 | 04-112513 | Miramar | Science Building - Renovate Classrooms to Labs/Add Wing
65 | N | 13220 | S.IV.3 | N.IV.1 | 04-112314 | Miramar | Student Services Center (Interim Library)
66 | N | 14120 | - | N.I.1 | - | CE | Clairemont/Linda Vista - Land Acquisition & Building (Land $1.8M)
67 | N | 14220 | - | N.II.1 | 04-111330 | CE | Educational Cultural Complex - Phase IIB Wing
68 | N | 11340 | S.V | N.III.2 | 04-112710 | City | Language/Speech/Visual Arts ("C" Building)
69 | N | 12420 | - | N.II.2 | 04-112803 | Mesa | Cafeteria and Bookstore / Stockroom
70 | N | 11430 | S.VI | N.IV.1 | 04-110878; 04-111010; 04-111216 | City | Infrastructure - Central Plant/Sewer & Storm Drain/Data & IT Projects
71 | N | 123*** | - | N.III | 04-112591; 04-112720; 04-113173 | Mesa | Infrastructure - Fire Lane/Central Plant/IT
72 | N | 13550 | - | N.IV.6 | - | Miramar | Campus Safety Enhancements
73 | N | 135** | - | N.V.1 | - | Miramar | Infrastructure - Phase II
74 | N | 15210 | - |  | N/A | District | Prop N Program Management | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
75 | N | 11330 | S.IV.1 | N.III.1 | - | City | "A" Building Renovation
76 | N | 11320 | S.VI | N.III.4 | - | City | "D" Building Roof
77 | N | 11250 | S.I.1 | N.I.2 | ? 04-100128 | City | Engineering Technology Building ("T" Building)
78 | N | 12120 | - | N.I.2 | - | Mesa | Center for Business and Technology
79 | N | 12520 | - | N.I.3 | - | Mesa | Fine Arts and Dramatic Arts
80 | N | 13650 | - | N.IV.4 | - | Miramar | Expansion of Maintenance Facilities
81 | N | 13680 | - |  | 04-113249 | Miramar | Remodel A-100 Building (CE Classrooms)
82 | N | 13170 | - |  | 04-113165 | Miramar | Remodel Existing Police Academy (A-200 Building)
83 | N | 11240 | S.I.3 | N.I.3 | 04-110503 | City | Business Technology Building
84 | N | 13180 | - | N.I.2 | - | Miramar | EVOC Driving Course
85 | N | 15220 | - | - | N/A | Reserve | Proposition N Reserve | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Old-X--Detail
DSA #
| 1 |  | DSA Cert Received
| 1 | A | Is the Certification in the DSA File?
| 1 | B | Is the Certification posted in SP?
| 2 |  | Subst Compl
Do ALL contracts have a clear substantial completion signed form in SP?
| 3 |  | Warranties
Do All contracts have warranties that match the substantial completion dates?
Are all warranties in SP?
| 4 |  | O&M's
|  | A | Do all O&M manuals appear located at DSC Archives?
|  | B | Are all O&M CD-Rom's saved on the District website?
| 5 |  | Record Docs
|  | A | Are as-built drawings turned over and located in DSC Archives?
|  | B | Are record drawings turned over and located in DSC Archives?
|  | C | Are record as-built Revit models provided and on the District servers?
|  | D | Is a COBie plan provided and on file?
| 6 |  | Contracts in SharePoint
| 7 |  | CO's + CCD's in SharePoint
| 8 |  | Minutes in SharePoint
| 9 |  | Photos in SharePoint
| 10 |  | Inspector Records on File (get from DSA Box if needed??)
| 11 |  | LEED Cert Received
|  | A | Does the USGBC site reflect a certification?
|  | B | What is the certification level?
| 12 |  | All NOC's Recorded
| 13 |  | All Paid
| 14 |  | CM13 / Datatel Reconciled
| 15 |  | Final Budget Adjustment
Warranties Filed / Logged?
O&M's Filed / Logged?
Columns |  |  | Date
System
Contractor
Physical Location
Digital Location
((level of detail for O&M components??))
Record BIM Model Received?
Record As-Builts Doc's Logged
COBiE Info Captured?
|  |  | CM13 Contracts in SharePoint | Action
(1) export CM13 contract list with $ value
CO's + CCD's in SharePoint
Minutes in SharePoint
Photos in SharePoint
IOR records in SP
LEED Cert Received
All NOC's in SP
Project Financially Closed?All Paid
All paid?
CM13 / Datatel reconciliation
Final budget adjustment
Lessons Learned?
Maint info ID'd (ie Perm BMPs, SF)
Incorporated into Campus Security Plan
` | `
From CM13 --
Will want for each project, at least:
all minutes
transmittals -- do an export of the logs with the description included (in lieu of having Kevin run a report?)
RFI - print request & answer log
RFI - check what RFI's are in SP - these will have drawings etc -- ideally all these will bein as-builts anyway
Contracts - do a CM13 to SP comparison
PO - run report
Insurance info report?
Daily report report / construction daily reports
WCR report -- and confirm that no money is left over
general notepad report
submittal log
RFI log